## Sheet1
Deviation | Possible Causes | Consequences
New regulatory - legislative requirements | Uncertainty in requirements, implications of pending/new changes in legislation AND Failure of Communication with regulators | None
New regulatory - legislative requirements | Uncertainty in requirements, implications of pending/new changes in legislation AND Failure of Member of MAC | None
New regulatory - legislative requirements | Uncertainty in requirements, implications of pending/new changes in legislation AND Failure of Attending briefing meetings held by regulators, Approvals Teams regarding Project design changes | None
New regulatory - legislative requirements | Uncertainty in requirements, implications of pending/new changes in legislation AND Failure of Legal opinions | None
New regulatory - legislative requirements AND Failure of Legal opinions | None | Greater financial requirements - to meet legislation changes
Late changes to Project design | Project change that results in additional as well as other regulatory requirements that are not identified earlier in the permitting phase AND Failure of Regulatory review, update permitting strategy for all Project design changes | None
Late changes to Project design | Project change that results in additional as well as other regulatory requirements that are not identified earlier in the permitting phase AND Failure of Prompt communication between Engineering, Approvals Teams regarding Project design changes | None
Late changes to Project design AND Failure of Prompt communication between Engineering, Approvals Teams regarding Project design changes | None | Delay in project approvals schedule
Insufficient Project design information to support regulatory process | Lack of effective, timely communication AND Failure of Maintaining Engineering Information Needs List to support effects assessment | None
Insufficient Project design information to support regulatory process | Project design not fully completed nor finalized AND Failure of Maintaining Engineering Information Needs List to support effects assessment | None
Insufficient Project design information to support regulatory process AND Failure of Developing, maintaining integrated project schedule | None | Delay in Project approvals schedule
Insufficient Project design information to support regulatory process | Lack of effective, timely communication AND Failure of Strong coordination between engineering, approvals team through regular meetings plus communications | None
Insufficient Project design information to support regulatory process AND Failure of Strong coordination between engineering, approvals team through regular meetings plus communications | None | Delay in project approvals schedule
Inadequate capacity of regulatory bodies to provide advice on scope of Project, permitting requirements AND Failure of Relationship management with regulators | None | Delay in project approvals schedule
Inadequate capacity of regulatory bodies to provide advice on scope of Project, permitting requirements AND Failure of Relationship management with regulators | None | Lack of service standards leading to inconsistent decision making
Inadequate capacity of regulatory bodies to provide advice on scope of Project, permitting requirements AND Failure of Relationship management with regulators | None | Unclear mandate
Inadequate capacity of regulatory bodies to provide advice on scope of Project, permitting requirements AND Failure of Communication with regulators | None | Delay in project approvals schedule
Inadequate capacity of regulatory bodies to provide advice on scope of Project, permitting requirements AND Failure of Communication with regulators | None | Lack of service standards leading to inconsistent decision making
Inadequate capacity of regulatory bodies to provide advice on scope of Project, permitting requirements AND Failure of Communication with regulators | None | Unclear mandate
Inadequate capacity of regulatory bodies to provide advice on scope of Project, permitting requirements | Inadequate knowledge transfer/mentoring of new staff AND Failure of Ensuring technically strong MMG approval team | None
Inadequate capacity of regulatory bodies to provide advice on scope of Project, permitting requirements AND Failure of Ensuring technically strong MMG approval team | None | Delay in project approvals schedule
Inadequate capacity of regulatory bodies to provide advice on scope of Project, permitting requirements AND Failure of Ensuring technically strong MMG approval team | None | Unclear mandate
Inadequate capacity of regulatory bodies to provide advice on scope of Project, permitting requirements AND Failure of Political engagement | None | Delay in Project approvals schedule
Inadequate capacity of regulatory bodies to provide advice on scope of Project, permitting requirements AND Failure of Political engagement | None | Lack of service standards leading to inconsistent decision making
Inadequate capacity of regulatory bodies to provide advice on scope of Project, permitting requirements AND Failure of Political engagement | None | Unclear mandate
Inadequate capacity of regulatory bodies to provide advice on scope of Project, permitting requirements | Increased workloads of regulatory bodies AND Failure of Political engagement | None
Inadequate capacity of regulatory bodies to provide advice on scope of Project, permitting requirements | Cutbacks of government staff AND Failure of Political engagement | None
Inadequate capacity of regulatory bodies to provide advice on scope of Project, permitting requirements | Increased workloads of regulatory bodies AND Failure of Partnership | None
Inadequate capacity of regulatory bodies to provide advice on scope of Project, permitting requirements | Cutbacks of government staff AND Failure of Partnership | None
Inadequate capacity of regulatory bodies to provide advice on scope of Project, permitting requirements | Inadequate knowledge transfer/mentoring of new staff AND Failure of Partnership | None
Inadequate capacity of regulatory bodies to provide advice on scope of Project, permitting requirements AND Failure of Partnership | None | Delay in project approvals schedule
Inadequate capacity of regulatory bodies to provide advice on scope of Project, permitting requirements | Increased workloads of regulatory bodies AND Failure of Cost sharing | None
Inadequate capacity of regulatory bodies to provide advice on scope of Project, permitting requirements | Cutbacks of government staff AND Failure of Cost sharing | None
Inadequate capacity of regulatory bodies to provide advice on scope of Project, permitting requirements | Inadequate knowledge transfer/mentoring of new staff AND Failure of Cost sharing | None
Inadequate capacity of regulatory bodies to provide advice on scope of Project, permitting requirements AND Failure of Cost sharing | None | Delay in project approvals schedule
Land use Plan contains land use designations not consistent with ICP's development objectives | NPC does not recognize ICP as grandfathered AND Failure of Communication with NPC | None
Land use Plan contains land use designations not consistent with ICP's development objectives AND Failure of Communication with NPC | None | Will require request for amendment to Land Use Plan
Land use Plan contains land use designations not consistent with ICP's development objectives | Project subject to Final NLUP due to delay in receiving Project Certificate AND Failure of Tracking progress of process | None
Land use Plan contains land use designations not consistent with ICP's development objectives AND Failure of Engaging experienced environmental support to ensure Project Certificate is received on schedule | None | Delay in project approvals schedule
Land use Plan contains land use designations not consistent with ICP's development objectives | Project subject to Final NLUP due to delay in receiving Project Certificate AND Failure of Having conformity with NBRLUP | None
Land use Plan contains land use designations not consistent with ICP's development objectives | Project subject to Final NLUP due to delay in receiving Project Certificate AND Failure of Engaging experienced environmental support to ensure Project Certificate is received on schedule | None
Large number of Information Requests IRs - Technical Comments on DEIS | Inadequate baseline information plus modelling to support DEIS conclusions AND Failure of Comprehensive environmental baseline programs | None
Large number of Information Requests IRs - Technical Comments on DEIS | Inadequate stakeholder consultation as well as TK/IQ collection to support DEIS AND Failure of Conduction of Community Forums | None
Large number of Information Requests IRs - Technical Comments on DEIS | Inadequate stakeholder consultation as well as TK/IQ collection to support DEIS AND Failure of Comprehensive TK/IQ program | None
Large number of Information Requests IRs - Technical Comments on DEIS | Increasing expectations of regulators, stakeholders in rigour of EA process AND Failure of Defensible EA methodology, effects analyses | None
Large number of Information Requests IRs - Technical Comments on DEIS | Inadequate stakeholder consultation as well as TK/IQ collection to support DEIS AND Failure of Integration of TK/IQ in all aspects of environmental assessment process | None
Large number of Information Requests IRs - Technical Comments on DEIS | Failure to communicate with NRCan regarding expectations for supporting information in DEIS AND Failure of Regulatory engagement plan - e.g. NRCan | None
Lack of a comprehensive - defensible alternative analysis | Misunderstood requirements for alternatives assessment AND Failure of Adherence to Environment Canada guidelines for assessing alternatives for mine waste disposal | None
Lack of a comprehensive - defensible alternative analysis | Lack of register for alternative evaluations AND Failure of Adherence to Environment Canada guidelines for assessing alternatives for mine waste disposal | None
Lack of a comprehensive - defensible alternative analysis | Lack of rigour for alternatives evaluations AND Failure of Adherence to Environment Canada guidelines for assessing alternatives for mine waste disposal | None
Lack of a comprehensive - defensible alternative analysis | Misunderstood requirements for alternatives assessment AND Failure of Strong coordination between engineering, approvals team through regular meetings plus communications | None
Lack of a comprehensive - defensible alternative analysis | Misunderstood requirements for alternatives assessment AND Failure of Ensuring technically strong MMG approval team | None
Lack of a comprehensive - defensible alternative analysis | Lack of register for alternative evaluations AND Failure of Ensuring technically strong MMG approval team | None
Lack of a comprehensive - defensible alternative analysis | Lack of rigour for alternatives evaluations AND Failure of Ensuring technically strong MMG approval team | None
Lack of a comprehensive - defensible alternative analysis | Misunderstood requirements for alternatives assessment AND Failure of Political engagement | None
Lack of a comprehensive - defensible alternative analysis AND Failure of Political engagement | None | Delay in permitting schedule
Lack of a comprehensive - defensible alternative analysis AND Failure of Political engagement | None | Miss initial year of construction
Lack of a comprehensive - defensible alternative analysis | Misunderstood requirements for alternatives assessment AND Failure of Active communication with communities | None
Lack of a comprehensive - defensible alternative analysis | Lack of register for alternative evaluations AND Failure of Active communication with communities | None
Lack of a comprehensive - defensible alternative analysis for road | Lack of transparency in alternative evaluations plus decision making with communities AND Failure of Active communication with communities | None
Lack of a comprehensive - defensible alternative analysis for road | Lack of transparency in alternative evaluations plus decision making with communities AND Failure of Communication with regulators | None
Lack of a comprehensive - defensible alternative analysis for road AND Failure of Strong coordination between engineering, approvals team through regular meetings plus communications | None | In absence of defensible rationale for road design, regulators plus communities may require additional mitigation that is Impractical/ infeasible
Non-conformity with EIS Guidelines | Inadequate concordance table, poor organization of DEIS AND Failure of Lessons learned from past applications regarding nonconformity | None
Non-conformity with EIS Guidelines | Not receiving NIRB EIS guidelines in a timely manner - insufficient lead time AND Failure of Lessons learned from past applications regarding nonconformity | None
Non-conformity with EIS Guidelines | Insufficient baseline AND Failure of Lessons learned from past applications regarding nonconformity | None
Non-conformity with EIS Guidelines | Lack of managing EIS guideline development AND Failure of Lessons learned from past applications regarding nonconformity | None
Non-conformity with EIS Guidelines | Failure to have detailed technical meetings with regulators plus communities in advance of guideline development AND Failure of Lessons learned from past applications regarding nonconformity | None
Non-conformity with EIS Guidelines | Lack of managing EIS guideline development AND Failure of Organizational structure | None
Non-conformity with EIS Guidelines | Inadequate concordance table, poor organization of DEIS AND Failure of Sharing of information in advance of guideline development | None
Non-conformity with EIS Guidelines | Not receiving NIRB EIS guidelines in a timely manner - insufficient lead time AND Failure of Sharing of information in advance of guideline development | None
Non-conformity with EIS Guidelines | Lack of managing EIS guideline development AND Failure of Sharing of information in advance of guideline development | None
Non-conformity with EIS Guidelines | Failure to have detailed technical meetings with regulators plus communities in advance of guideline development AND Failure of Sharing of information in advance of guideline development | None
Non-conformity with EIS Guidelines | Insufficient baseline AND Failure of Partnership | None
Non-conformity with EIS Guidelines | Not receiving NIRB EIS guidelines in a timely manner - insufficient lead time AND Failure of Collaboration in field work | None
Non-conformity with EIS Guidelines | Lack of managing EIS guideline development AND Failure of Collaboration in field work | None
Non-conformity with EIS Guidelines | Failure to have detailed technical meetings with regulators plus communities in advance of guideline development AND Failure of Collaboration in field work | None
Delay in receiving Type A Water License | Non-conformity with NWB application requirements AND Failure of Coordinated NIRB/ NWB process | None
Delay in receiving Type A Water License | Insufficient engineering to support NWB/NIRB review process AND Failure of Coordinated NIRB/ NWB process | None
Delay in receiving Type A Water License | Non-conformity with NWB application requirements AND Failure of Communication with NWB to ensure Draft EIS provides all required information as part of coordinated process | None
Delay in receiving Type A Water License | Insufficient engineering to support NWB/NIRB review process AND Failure of Communication with NWB to ensure Draft EIS provides all required information as part of coordinated process | None
Delay in receiving Type A Water License | Insufficient engineering to support NWB/NIRB review process AND Failure of Good information about surface water - groundwater quality - quantity | None
Delay in receiving Type A Water License | Inadequate baseline to support closure plan AND Failure of Good information about surface water - groundwater quality - quantity | None
Delay in receiving Type A Water License | Insufficient engineering to support NWB/NIRB review process AND Failure of Good information on mineral waste | None
Delay in receiving Type A Water License | Inadequate baseline to support closure plan AND Failure of Good information on mineral waste | None
Unsuccessful in concluding Water Compensation Agreement in timely manner requiring arbitaration by NWB plus delaying Water License | Disagreement on scope of agreement plus financial compensation model AND Failure of Effective communication/consultation with KIA regarding water compensation agreement early in permitting process | None
Navigational safety along shipping corridor AND Failure of Shipping Management Plan - adherance to international shipping regulations | None | Navigational hazards, inaccessibility of channels, straits that have typically been clear of ice during summer due to ice movement
Navigational safety along shipping corridor AND Failure of Shipping Management Plan - adherance to international shipping regulations | None | Increased expectations regarding mitigation - e.g., spill response
Navigational safety along shipping corridor AND Failure of Ice Management Plan | None | Navigational hazards, inaccessibility of channels, straits that have typically been clear of ice during summer due to ice movement
Navigational safety along shipping corridor | Lack of adequate bathymetry AND Failure of Collection of additional bathymetric data to ensure that MMG can demonstrate to regulators plus communities that MMG has adequate mapping of shipping routes - alleviate concerns related to potential marine spills | None
Navigational safety along shipping corridor AND Failure of Collection of additional bathymetric data to ensure that MMG can demonstrate to regulators plus communities that MMG has adequate mapping of shipping routes - alleviate concerns related to potential marine spills | None | Navigational hazards, inaccessibility of channels, straits that have typically been clear of ice during summer due to ice movement
Unsuccessful in obtaining approvals for pre-development works to support early staging/ pre-construction activities | Lack of confidence in NIRB with progress being made in the EA process - extent of IRs plus technical comments, quality of information supporting the DEIS, quality of EMPs work - AND Failure of Robust environmental baseline | None
Unsuccessful in obtaining approvals for pre-development works to support early staging/ pre-construction activities | Nature plus extent of activities planned as predevelopment AND Failure of Comprehensive plans for environmental management | None
Unsuccessful in obtaining approvals for pre-development works to support early staging/ pre-construction activities | Lack of confidence in NIRB with progress being made in the EA process - extent of IRs plus technical comments, quality of information supporting the DEIS, quality of EMPs - work AND Failure of Comprehensive plans for environmental management | None
Unsuccessful in obtaining approvals for pre-development works to support early staging/ pre-construction activities | Lack of confidence in NIRB with progress being made in the EA process - extent of IRs plus technical comments, quality of information supporting the DEIS, quality of EMPs - work AND Failure of Early plus consistent consultation with NIRB | None
Unsuccessful in obtaining approvals for pre-development works to support early staging/ pre-construction activities | Lack of confidence in NIRB with progress being made in the EA process - extent of IRs plus technical comments, quality of information supporting the DEIS, quality of EMPs - work AND Failure of Consultation with KIA | None
Destruction - disturbance of archaeological resources during construction plus operations | Inadequate/incomplete archaeological survey coverage AND Failure of Completion of comprehensive archaeological surveys once Project footprint finalized | None
Destruction - disturbance of archaeological resources during construction plus operations AND Failure of Site-specific archaeological mitigation plans approved by the GN | None | Delay in Construction
Destruction - disturbance of archaeological resources during construction plus operations AND Failure of Site-specific archaeological mitigation plans approved by the GN | None | Delay in operational activities to allow for site evaluation plus site mitigation
Destruction - disturbance of archaeological resources during construction plus operations AND Failure of Site-specific archaeological mitigation plans approved by the GN | None | Reputational damage
Destruction - disturbance of archaeological resources during construction plus operations AND Failure of Site-specific archaeological mitigation plans approved by the GN | None | Non-compliance with cultural heritage legal obligations
Destruction - disturbance of archaeological resources during construction plus operations AND Failure of Site-specific archaeological mitigation plans approved by the GN | None | Not meeting social obligations
Destruction - disturbance of archaeological resources during construction plus operations | Change in project design AND Failure of Buffering project footprint for baseline to adequately cover for any changes in project - alternatives | None
Destruction - disturbance of archaeological resources during construction plus operations AND Failure of Preparing measures to reinforce importance of arch sites in communities - e.g., Community Forums | None | Reputational damage
Destruction - disturbance of archaeological resources during construction plus operations AND Failure of Preparing measures to reinforce importance of arch sites in communities - e.g., Community Forums | None | Non-compliance with cultural heritage legal obligations
Destruction - disturbance of archaeological resources during construction plus operations AND Failure of Preparing measures to reinforce importance of arch sites in communities - e.g., Community Forums | None | Not meeting social obligations
Destruction - disturbance of archaeological resources during construction plus operations | Buffering project footprint for baseline to adequately cover for any changes in project - alternatives AND Failure of Working with CLEY to ensure adequate mitigation for significant sites | None
Destruction - disturbance of archaeological resources during construction plus operations | Site-specific archaeological mitigation plans approved by the GN AND Failure of Working with CLEY to ensure adequate mitigation for significant sites | None
Destruction - disturbance of archaeological resources during construction plus operations | Not meeting social obligations AND Failure of Working with CLEY to ensure adequate mitigation for significant sites | None
Attraction of international plus national media attention to caribou plus MMER related issues | Ineffective issue management AND Failure of DFH providing strategic advice with respect to corporate communications plus public affairs | None
Attraction of international plus national media attention to caribou plus MMER related issues | Ineffective issue management AND Failure of Effort to understanding issues with communities | None
Attraction of international plus national media attention to caribou plus MMER related issues AND Failure of Effort to understanding issues with communities | None | Lack of social license
Attraction of international plus national media attention to caribou plus MMER related issues | Ineffective issue management AND Failure of Robust alternatives assessment | None
Attraction of international plus national media attention to caribou plus MMER related issues AND Failure of Robust alternatives assessment | None | Delay in project approvals schedule
Attraction of international plus national media attention to caribou plus MMER related issues | Ineffective issue management AND Failure of Reaching out to NGOs plus First Nations | None
Attraction of international plus national media attention to caribou plus MMER related issues AND Failure of Reaching out to NGOs plus First Nations | None | Lack of social license
Inadequate consultation with transboundary First Nations - NWT, Sask | Under-estimate influence of transboundary First Nations in NIRB review process AND Failure of Development of an Aborginal Consultation strategy - due diligence in meetings with First Nations groups within the NWT that have demonstrated an interest in the Project plus gain clarity of Crown in this matter | None
Inadequate consultation with transboundary First Nations - NWT, Sask AND Failure of Maintaining working relationship with NPMO | None | Reputational damage
Inadequate consultation with transboundary First Nations - NWT, Sask AND Failure of Maintaining working relationship with NPMO | None | Lack of social license
Inadequate consultation with transboundary First Nations - NWT, Sask AND Failure of Maintaining working relationship with NPMO | None | Legal undertakings
Coming later in review process | NIRB review schedule for regional mining projects AND Failure of Distinquishing the ICP from other regional projects | None
Coming later in review process AND Failure of Avoiding having to consider far future development scenarios in CEA | None | Increased mitigation to address CE - e.g. use of BIPAR
Coming later in review process AND Failure of Defensible cumulative effects methodology | None | Increased mitigation to address CE - e.g. use of BIPAR
Delay in reaching final agreements with KIA on IIBA | Inability to negotiate mutually acceptable agreements AND Failure of Effective communication/consulation with KIA early in permitting process | None
Delay in reaching final agreements with KIA on IIBA AND Failure of Effective communication/consultation with KIA early in permitting process | None | Delay in construction
Linking of IIBA to issuance of land tenure for IOL lands | Inadequate consultation with KIA AND Failure of Effective communication/consultation with KIA early in permitting process | None
Linking of IIBA to issuance of land tenure for IOL lands | Inadequate consultation with KIA AND Failure of Encouraging KIA to separate IIBA from land tenure, First right of refusal on land package | None
Linking of IIBA to issuance of land tenure for IOL lands | Inability to negotiate a mutually acceptable IIBA in a timely manner AND Failure of Encouraging KIA to separate IIBA from land tenure, First right of refusal on land package | None
Linking of IIBA to issuance of land tenure for IOL lands | Land tenure issued to another proponent with interest within the Izok corridor - e.g., Ulu AND Failure of Encouraging KIA to separate IIBA from land tenure, First right of refusal on land package | None
Linking of IIBA to issuance of land tenure for IOL lands | Land tenure issued to another proponent with interest within the Izok corridor - e.g., Ulu AND Failure of Tracking status of other projects | None
Uncertainty in reclamation security requirements for NWB, DIOs plus leases | Divided jurisdiction over surface lands - DIOs vs. Crown plus concurrent jurisdiction of the NWB over water resources AND Failure of Working through MAC plus NWT plus Nunavut Chamber of Mines to apply pressure on NWB to resolve issue of double bonding | None
Uncertainty in reclamation security requirements for NWB, DIOs plus leases | Lack of agreement on how DIO plus Government of Canada share management control over the reclamation security AND Failure of Working through MAC plus NWT plus Nunavut Chamber of Mines to apply pressure on NWB to resolve issue of double bonding | None
Uncertainty in reclamation security requirements for NWB, DIOs plus leases AND Failure of Progressive reclamation | None | Duplicate - overlapping requirements for reclamation security
Uncertainty in reclamation security requirements for NWB, DIOs plus leases | Divided jurisdiction over surface lands - DIOs vs. Crown plus concurrent jurisdiction of the NWB over water resources | None
Project effects - e.g. food insecurity due to effecs on Bathurst caribou herd, changes in environmental health access restrictions to traditional areas | Inadequate consultation AND Failure of Consultation strategy including meetings with First Nations groups within the NWT that have demonstrated an interest in the Project | None
Project effects - e.g. food insecurity due to effecs on Bathurst caribou herd, changes in environmental health access restrictions to traditional areas | Lack of agreement with First Nations on how best to address/resolve concern AND Failure of Consultation strategy including meetings with First Nations groups within the NWT that have demonstrated an interest in the Project | None
Project effects - e.g. food insecurity due to effecs on Bathurst caribou herd, changes in environmental health access restrictions to traditional areas AND Failure of Consultation strategy includes meetings with First Nations groups within the NWT that have demonstrated an interest in the Project | None | Delay in project
Project effects - e.g. food insecurity due to effecs on Bathurst caribou herd, changes in environmental health access restrictions to traditional areas AND Failure of Consultation strategy includes meetings with First Nations groups within the NWT that have demonstrated an interest in the Project | None | Not meeting social obligations
Project effects - e.g. food insecurity due to effecs on Bathurst caribou herd, changes in environmental health access restrictions to traditional areas AND Failure of Consultation strategy includes meetings with First Nations groups within the NWT that have demonstrated an interest in the Project | None | Reputational Damage
Project effects - e.g. food insecurity due to effecs on Bathurst caribou herd, changes in environmental health access restrictions to traditional areas | Lack of agreement with First Nations on how best to address/resolve concern AND Failure of Working with NMPO to address aboriginal rights issues | None
Project effects - e.g. food insecurity due to effecs on Bathurst caribou herd, changes in environmental health access restrictions to traditional areas AND Failure of Working with NMPO to address aboriginal rights issues | None | Accomodation required
Natural events - winter conditions, flooding AND Failure of Occupational Health - Safety Management Plan | None | Stoppage of work
Natural events - winter conditions, flooding AND Failure of Occupational Health - Safety Management Plan | None | Injuries/fatalities
Natural events - winter conditions, flooding AND Failure of Emergency Response Plan | None | Stoppage of work
Natural events - winter conditions, flooding AND Failure of Emergency Response Plan | None | Delays in schedules
Natural events - winter conditions, flooding AND Failure of Emergency Response Plan | None | Injuries/fatalities
Natural events - winter conditions, flooding AND Failure of Emergency Response Plan | None | Cost of equipment/ infrastructure repair/ replacement
Natural events - winter conditions, flooding AND Failure of Road Management Plan | None | Delays in schedules
Natural events - winter conditions, flooding AND Failure of Road Management Plan | None | Injuries/fatalities
Natural events - winter conditions, flooding AND Failure of Road Management Plan | None | Cost of equipment/ infrastructure repair/ replacement
Natural events - winter conditions, flooding AND Failure of Project design | None | Delays in schedules
Natural events - winter conditions, flooding AND Failure of Project design | None | Cost of equipment/ infrastructure repair/ replacement
Natural events - winter conditions, flooding AND Failure of Worker training | None | Stoppage of work
Natural events - winter conditions, flooding AND Failure of Worker training | None | Delays in schedules
Natural events - winter conditions, flooding AND Failure of Worker training | None | Injuries/fatalities
Natural events - winter conditions, flooding AND Failure of Worker training | None | Cost of equipment/ infrastructure repair/ replacement
Vehicle incident | Use of same road by large haul trucks plus smaller personnel vehicles AND Failure of Road Management Plan - e.g., communication system | None
Vehicle incident | Inclement weather AND Failure of Road Management Plan - e.g., communication system | None
Vehicle incident | Poor visibility due to road design AND Failure of Road Management Plan - e.g., communication system | None
Vehicle incident | Excessive vehicle speeds AND Failure of Road Management Plan - e.g., communication system | None
Vehicle incident | Wildlife collision AND Failure of Road Management Plan - e.g., communication system | None
Vehicle incident | Road communication system failure AND Failure of Road Management Plan - e.g., communication system | None
Vehicle incident AND Failure of Spill contingency plan | None | Contamination of ground plus surface waters
Vehicle incident AND Failure of Spill contingency plan | None | Fines - penalties
Vehicle incident | Excessive vehicle speeds AND Failure of Worker Training | None
Vehicle incident | Human error AND Failure of Worker Training | None
Vehicle incident | Poor inspection/maintenance of vehicles AND Failure of Worker Training | None
Vehicle incident | Use of same road by large haul trucks plus smaller personnel vehicles AND Failure of Road Design | None
Vehicle incident | Poor visibility due to road design AND Failure of Road Design | None
Vehicle incident | Excessive vehicle speeds AND Failure of Road Design | None
Vehicle incident | Failure of communication system for road AND Failure of Road Design | None
Vehicle incident AND Failure of Emergency shelters | None | Injuries/fatalities
Shortage of skilled workers | Industry competition AND Failure of Recruitment & Retention Plan | None
Shortage of skilled workers | Lack of interest in working in North AND Failure of Recruitment & Retention Plan | None
Shortage of skilled workers | Lack of skilled Canadian workers for underground AND Failure of Recruitment & Retention Plan | None
Shortage of skilled workers AND Failure of Recruitment & Retention Plan | None | Delay in construction
Shortage of skilled workers AND Failure of Recruitment & Retention Plan | None | Delay in operations
Shortage of skilled workers | Lack of funding for training of youth AND Failure of MMG involvement in mine training programs | None
Shortage of skilled workers | Industry competition AND Failure of MMG involvement in mine training programs | None
Shortage of skilled workers | Lack of skilled Canadian workers for underground AND Failure of MMG involvement in mine training programs | None
Higher personnel turnover than expected | Remote, harsh working environment AND Failure of Employee Well-being Enhancement Program | None
Higher personnel turnover than expected | Remote, harsh working environment AND Failure of Recruitment & Retention Plan | None
Higher personnel turnover than expected | Industry competition AND Failure of Recruitment & Retention Plan | None
Higher personnel turnover than expected | Remote, harsh working environment AND Failure of Human Resources Management Plan | None
Higher personnel turnover than expected | Industry competition AND Failure of Human Resources Management Plan | None
Lack of MMG profile in Canada AND Failure of Recruitment & Retention Plan | None | Delay in construction
Lack of MMG profile in Canada AND Failure of Recruitment & Retention Plan | None | Increased recruitment costs
Lack of MMG profile in Canada | Inadequate corporate communications AND Failure of External Relations | None
Lack of MMG profile in Canada | Inadequate corporate communications AND Failure of Human Resources Management Plan | None
Lack of MMG profile in Canada AND Failure of Human Resources Management Plan | None | Delay in construction
Lack of MMG profile in Canada AND Failure of Human Resources Management Plan | None | Increased Recruitment costs
A significant fire at the Project | Human error AND Failure of Hazard Identification & Risk Assessment | None
A significant fire at the Project | Equipment failure AND Failure of Hazard Identification & Risk Assessment | None
A significant fire at the Project AND Failure of Hazard Identification & Risk Assessment | None | Safety & health risk
A significant fire at the Project | Human error AND Failure of Occupational Health - Safety Management Plan | None
A significant fire at the Project | Equipment failure AND Failure of Occupational Health - Safety Management Plan | None
A significant fire at the Project AND Failure of Occupational Health - Safety Management Plan | None | Safety & health risk
A significant fire at the Project AND Failure of Emergency Response Plan | None | Safety & health risk
A significant fire at the Project | Equipment failure AND Failure of Equipment Inspection - Maintenance | None
A significant fire at the Project AND Failure of Equipment Inspection - Maintenance | None | Safety & health risk
A significant fire at the Project | Human error AND Failure of Worker Training | None
A significant fire at the Project AND Failure of Worker safety training | None | Safety & health risk
Lack of logistical & emergency support AND Failure of Emergency medical service providers - Medivac | None | Inability to access proper medical care
Lack of logistical & emergency support AND Failure of Emergency medical service providers - Medivac | None | Safety & health risk
Lack of logistical & emergency support | Unavailability of aircraft AND Failure of Appropriate staff & resources | None
Lack of logistical & emergency support AND Failure of Appropriate staff & resources | None | Safety & health risk
Outbreak of infectious disease | Lack of disease control & detection AND Failure of Human Health Emergency Management Plan | None
Outbreak of infectious disease AND Failure of Human Health Emergency Management Plan | None | Human safety risk
Outbreak of infectious disease AND Failure of Human Health Emergency Management Plan | None | Reduce staffing capacity
Ongoing liability to MMG for closure & post-closure hazards | Inadequate closure planning AND Failure of Adequate closure plan | None
Ongoing liability to MMG for closure & post-closure hazards AND Failure of Monitoring of risks | None | Human safety risk
Ongoing liability to MMG for closure & post-closure hazards | Lack of security AND Failure of Monitoring of risks | None
Worker health & safety from exposure to concentrate dust - fumes in concentrate storage shed AND Failure of Fogging of concentrate piles to reduce dust generation | None | Acute & chronic health hazard - inhalation of dust, sulphur dioxide gas, lead & zinc oxide fumes
Worker health & safety from exposure to concentrate dust - fumes in concentrate storage shed AND Failure of Fogging of concentrate piles to reduce dust generation | None | Fugitive dust from shed
Worker health & safety from exposure to concentrate dust - fumes in concentrate storage shed AND Failure of Hazard Identification & Risk Assessment | None | Acute & chronic health hazard - inhalation of dust, sulphur dioxide gas, lead & zinc oxide fumes
Worker health & safety from exposure to concentrate dust - fumes in concentrate storage shed AND Failure of Hazard Identification & Risk Assessment | None | Fugitive dust from shed
Worker health & safety from exposure to concentrate dust - fumes in concentrate storage shed | Inadequate PPE AND Failure of Occupational Health - Safety Management Plan | None
Worker health & safety from exposure to concentrate dust - fumes in concentrate storage shed | Inadequate training AND Failure of Occupational Health - Safety Management Plan | None
Worker health & safety from exposure to concentrate dust - fumes in concentrate storage shed | Inability to meet target moisture level in concentrate AND Failure of Monitoring & testing of concentrate piles | None
Worker health & safety from exposure to concentrate dust - fumes in concentrate storage shed | Inadequate monitoring AND Failure of Monitoring & testing of concentrate piles | None
Worker health & safety from exposure to concentrate dust - fumes in concentrate storage shed AND Failure of Monitoring & testing of concentrate piles | None | Acute & chronic health hazard - inhalation of dust, sulphur dioxide gas, lead & zinc oxide fumes
Worker health & safety from exposure to concentrate dust - fumes in concentrate storage shed | Inadequate PPE AND Failure of Use of appropriate respiratory protection equipment | None
Worker health & safety from exposure to concentrate dust - fumes in concentrate storage shed AND Failure of Use of appropriate respiratory protection equipment | None | Acute & chronic health hazard - inhalation of dust, sulphur dioxide gas, lead & zinc oxide fumes
Worker health & safety from exposure to concentrate dust - fumes in concentrate storage shed AND Failure of Medical services | None | Acute & chronic health hazard - inhalation of dust, sulphur dioxide gas, lead & zinc oxide fumes
Worker health & safety from exposure to concentrate dust - fumes in concentrate storage shed | Inability to meet target moisture level in concentrate AND Failure of Sealing concentrate from air | None
Worker health & safety from exposure to concentrate dust - fumes in concentrate storage shed | Self-heating of concentrate AND Failure of Sealing concentrate from air | None
Worker health & safety from exposure to concentrate dust - fumes in concentrate storage shed AND Failure of Sealing concentrate from air | None | Acute & chronic health hazard - inhalation of dust, sulphur dioxide gas, lead & zinc oxide fumes
Worker health & safety from exposure to concentrate dust - fumes in concentrate storage shed AND Failure of Sealing concentrate from air | None | Fugitive dust from shed
Worker health & safety from exposure to concentrate dust - fumes in concentrate storage shed | Inadequate training AND Failure of Worker training | None
Worker health & safety from exposure to concentrate dust - fumes in concentrate storage shed | Inadequate monitoring AND Failure of Worker supervision | None
Worker health & safety from exposure to concentrate dust - fumes in concentrate storage shed | Inadequate monitoring AND Failure of Worker supervision | None
Worker health & safety from exposure to concentrate dust - fumes in concentrate storage shed | Inadequate training AND Failure of Worker Supervision | None
Not meeting water quality objectives at Izok at post-closure could lead to longer post-closure phase | Underestimate water treatment requirements - duration AND Failure of Signoff - approval of design | None
Not meeting water quality objectives at Izok at post-closure could lead to longer post-closure phase | Inadequate water treatment technology AND Failure of Signoff - approval of design | None
Not meeting water quality objectives at Izok at post-closure could lead to longer post-closure phase AND Failure of Signoff - approval of design | None | Regulatory non-compliance
Not meeting water quality objectives at Izok at post-closure could lead to longer post-closure phase | Underestimate water treatment requirements - duration AND Failure of Water Management Plan - monitoring - maintenance | None
Not meeting water quality objectives at Izok at post-closure could lead to longer post-closure phase | Inadequate water treatment technology AND Failure of Water Management Plan - monitoring - maintenance | None
Not meeting water quality objectives at Izok at post-closure could lead to longer post-closure phase | Cost of meeting water quality objectives AND Failure of Water Management Plan - monitoring - maintenance | None
Not meeting water quality objectives at Izok at post-closure could lead to longer post-closure phase AND Failure of Water Management Plan - monitoring - maintenance | None | Regulatory non-compliance
Not meeting water quality objectives at Izok at post-closure could lead to longer post-closure phase AND Failure of Water Management Plan - monitoring - maintenance | None | Increased costs associated with longer post-closure monitoring
Not meeting water quality objectives at Izok at post-closure could lead to longer post-closure phase AND Failure of Water Management Plan - monitoring - maintenance | None | Increased costs associated with longer post-closure water treatment
Not meeting water quality objectives at Izok at post-closure could lead to longer post-closure phase | Underestimate water treatment requirements - duration AND Failure of Correct Site Water balance | None
Not meeting water quality objectives at Izok at post-closure could lead to longer post-closure phase | Inadequate water treatment technology AND Failure of Correct Site Water balance | None
Not meeting water quality objectives at Izok at post-closure could lead to longer post-closure phase AND Failure of Correct Site Water balance | None | Regulatory non-compliance
Not meeting water quality objectives at Izok at post-closure could lead to longer post-closure phase AND Failure of Correct Site Water balance | None | Increased costs associated with longer post-closure monitoring
Not meeting water quality objectives at Izok at post-closure could lead to longer post-closure phase AND Failure of Correct Site Water balance | None | Increased costs associated with longer post-closure water treatment
Not meeting water quality objectives at Izok at post-closure could lead to longer post-closure phase | Underestimate water treatment requirements - duration AND Failure of Good information about surface - ground water quality - quantity, - waste water streams | None
Not meeting water quality objectives at Izok at post-closure could lead to longer post-closure phase | Inadequate water treatment technology AND Failure of Good information about surface - ground water quality - quantity, - waste water streams | None
Not meeting water quality objectives at Izok at post-closure could lead to longer post-closure phase AND Failure of Good information about surface - ground water quality - quantity, - waste water streams | None | Signoff - approval of design
Not meeting water quality objectives at Izok at post-closure could lead to longer post-closure phase AND Failure of Good information about surface - ground water quality - quantity, - waste water streams | None | Increased costs associated with longer post-closure monitoring
Not meeting water quality objectives at Izok at post-closure could lead to longer post-closure phase AND Failure of Good information about surface - ground water quality - quantity, - waste water streams | None | Increased costs associated with longer post-closure water treatment
Not meeting water quality objectives at Izok at post-closure could lead to longer post-closure phase | Inadequate water treatment technology AND Failure of Communication/negotiations with regulators related to reasonable parameters - objectives | None
Not meeting water quality objectives at Izok at post-closure could lead to longer post-closure phase AND Failure of Communication/negotiations with regulators related to reasonable parameters - objectives | None | Regulatory non-compliance
Not meeting water quality objectives at Izok at post-closure could lead to longer post-closure phase AND Failure of Communication/negotiations with regulators related to reasonable parameters - objectives | None | Increased bonding requirements associated with water license renewal
Not meeting water quality objectives at Izok at post-closure could lead to longer post-closure phase | Underestimate water treatment requirements - duration AND Failure of Worker Training | None
Not meeting water quality objectives at Izok at post-closure could lead to longer post-closure phase | Inadequate water treatment technology AND Failure of Worker Training | None
Not meeting water quality objectives at Izok at post-closure could lead to longer post-closure phase | Underestimate water treatment requirements - duration AND Failure of Adequate geochemistry data | None
Not meeting water quality objectives at Izok at post-closure could lead to longer post-closure phase | Inadequate water treatment technology AND Failure of Adequate geochemistry data | None
Not meeting water quality objectives at Izok at post-closure could lead to longer post-closure phase | Cost of meeting water quality objectives AND Failure of Adequate geochemistry data | None
Not meeting water quality objectives at Izok at post-closure could lead to longer post-closure phase AND Failure of Adequate geochemistry data | None | Regulatory non-compliance
Lack of geochemical data for the port could cause ARD - ML issues | Inadequate characterization of subsurface conditions AND Failure of Geochemical testing within Project footprint of diversion channel | None
Lack of geochemical data for the port could cause ARD - ML issues AND Failure of Geochemical testing within Project footprint of diversion channel | None | Adverse effects on marine resources - habitat
Lack of geochemical data for the port could cause ARD - ML issues AND Failure of Mineral Waste Management Plan | None | Fines - penalties for non-compliance
Lack of geochemical data for the port could cause ARD - ML issues AND Failure of Mineral Waste Management Plan | None | Deterioration in relationship with regulator
Lack of geochemical data for the port could cause ARD - ML issues AND Failure of Mineral Waste Management Plan | None | Reputational damage
Lack of geochemical data for the port could cause ARD - ML issues AND Failure of Mineral Waste Management Plan | None | Adverse effects on marine resources - habitat
Excavation/exposure of PAG during construction of the Izok diversion channel could result in ARD - metal leaching | Incorrect handling of PAG material during construction AND Failure of Geochemical testing within Project footprint of diversion channel | None
Excavation/exposure of PAG during construction of the Izok diversion channel could result in ARD - metal leaching AND Failure of Geochemical testing within Project footprint of diversion channel | None | Regulatory non-compliance
Excavation/exposure of PAG during construction of the Izok diversion channel could result in ARD - metal leaching AND Failure of Geochemical testing within Project footprint of diversion channel | None | Adverse effects on surface water quality within - downsteam of the channel
Excavation/exposure of PAG during construction of the Izok diversion channel could result in ARD - metal leaching AND Failure of Geochemical testing within Project footprint of diversion channel | None | Adverse effects on fish habitat within - downstream of the channel
Excavation/exposure of PAG during construction of the Izok diversion channel could result in ARD - metal leaching AND Failure of Mineral Waste Management Plan | None | Regulatory non-compliance
Excavation/exposure of PAG during construction of the Izok diversion channel could result in ARD - metal leaching AND Failure of Mineral Waste Management Plan | None | Deterioration in relationship with regulator
Excavation/exposure of PAG during construction of the Izok diversion channel could result in ARD - metal leaching AND Failure of Mineral Waste Management Plan | None | Reputational damage
Excavation/exposure of PAG during construction of the Izok diversion channel could result in ARD - metal leaching AND Failure of Mineral Waste Management Plan | None | Delay in construction
Excavation/exposure of PAG during construction of the Izok diversion channel could result in ARD - metal leaching AND Failure of Mineral Waste Management Plan | None | Adverse effects on surface water quality within - downsteam of the channel
Excavation/exposure of PAG during construction of the Izok diversion channel could result in ARD - metal leaching AND Failure of Mineral Waste Management Plan | None | Adverse effects on fish habitat within - downstream of the channel
Excavation/exposure of PAG during construction of the Izok diversion channel could result in ARD - metal leaching AND Failure of Alternatives evaluation for location of diversion channel | None | Delay in construction
Excavation/exposure of PAG during construction of the Izok diversion channel could result in ARD - metal leaching AND Failure of Alternatives evaluation for location of diversion channel | None | Adverse effects on surface water quality within - downsteam of the channel
Excavation/exposure of PAG during construction of the Izok diversion channel could result in ARD - metal leaching AND Failure of Alternatives evaluation for location of diversion channel | None | Adverse effects on fish habitat within - downstream of the channel
Excavation/exposure of PAG during construction of the Izok Road - borrow pits could result in ARD - metal leaching | Incorrect handling of PAG material during construction AND Failure of Site supervision | None
Excavation/exposure of PAG during construction of the Izok Road - borrow pits could result in ARD - metal leaching | Inadequate characterization of PAG - NAG AND Failure of Site supervision | None
Excavation/exposure of PAG during construction of the Izok Road - borrow pits could result in ARD - metal leaching | Incorrect handling of PAG material during construction AND Failure of Worker Training | None
Excavation/exposure of PAG during construction of the Izok Road - borrow pits could result in ARD - metal leaching | Inadequate characterization of PAG - NAG AND Failure of Worker Training | None
Excavation/exposure of PAG during construction of the Izok Road - borrow pits could result in ARD - metal leaching AND Failure of Worker Training | None | Non-compliance
Excavation/exposure of PAG during construction of the Izok Road - borrow pits could result in ARD - metal leaching | Inadequate characterization of PAG - NAG AND Failure of Geochemical testing of borrow pits | None
Excavation/exposure of PAG during construction of the Izok Road - borrow pits could result in ARD - metal leaching AND Failure of Geochemical testing of borrow pits | None | Adverse effects on surface water qualirty within nearby streams - rivers
Excavation/exposure of PAG during construction of the Izok Road - borrow pits could result in ARD - metal leaching AND Failure of Geochemical testing of borrow pits | None | Adverse effects on fish - fish habitat within in nearby streams - rivers.
Excavation/exposure of PAG during construction of the Izok Road - borrow pits could result in ARD - metal leaching | Incorrect handling of PAG material during construction AND Failure of Mineral Waste Management Plan | None
Excavation/exposure of PAG during construction of the Izok Road - borrow pits could result in ARD - metal leaching AND Failure of Mineral Waste Management Plan | None | Adverse effects on surface water qualirty within nearby streams - rivers
Excavation/exposure of PAG during construction of the Izok Road - borrow pits could result in ARD - metal leaching AND Failure of Mineral Waste Management Plan | None | Adverse effects on fish - fish habitat within in nearby streams - rivers.
Excavation/exposure of PAG during construction of the Izok Road - borrow pits could result in ARD - metal leaching AND Failure of Mineral Waste Management Plan | None | Non-compliance
Inappropriate infilling with PAG causing ARD - metal leaching | Human error AND Failure of Site supervision | None
Inappropriate infilling with PAG causing ARD - metal leaching AND Failure of Site supervision | None | Contamination of surface waters
Inappropriate infilling with PAG causing ARD - metal leaching AND Failure of Site supervision | None | Contamination - adverse effects on fish - fish habitat
Inappropriate infilling with PAG causing ARD - metal leaching | Inadequate characterization of PAG - NAG AND Failure of Worker training | None
Inappropriate infilling with PAG causing ARD - metal leaching | Human error AND Failure of Worker training | None
Inappropriate infilling with PAG causing ARD - metal leaching AND Failure of Worker training | None | Contamination of surface waters
Inappropriate infilling with PAG causing ARD - metal leaching AND Failure of Worker training | None | Contamination - adverse effects on fish - fish habitat
Inappropriate infilling with PAG causing ARD - metal leaching | Inadequate characterization of PAG - NAG AND Failure of Geochemical testing | None
Inappropriate infilling with PAG causing ARD - metal leaching AND Failure of Geochemical testing | None | Contamination of surface waters
Inappropriate infilling with PAG causing ARD - metal leaching AND Failure of Geochemical testing | None | Contamination - adverse effects on fish - fish habitat
Inappropriate dumping of PAG into NAG pile causing ARD - metal leaching | Human error AND Failure of Site supervision | None
Inappropriate dumping of PAG into NAG pile causing ARD - metal leaching | Human error AND Failure of Worker training | None
Inappropriate dumping of PAG into NAG pile causing ARD - metal leaching | Inadequate characterization of PAG - NAG AND Failure of Worker training | None
Handling - transport of tailings could cause dust emissions | Improper handling procedures AND Failure of Covers on trucks | None
Handling - transport of tailings could cause dust emissions AND Failure of Covers on trucks | None | Transboundary contamination of surface water
Handling - transport of tailings could cause dust emissions AND Failure of Covers on trucks | None | Transboundary contamination of ground water
Handling - transport of tailings could cause dust emissions AND Failure of Covers on trucks | None | Transboundary contamination of air water
Handling - transport of tailings could cause dust emissions AND Failure of Covers on trucks | None | Occupational health risk
Handling - transport of tailings could cause dust emissions AND Failure of 15% moisture content of tailings | None | Transboundary contamination of surface water
Handling - transport of tailings could cause dust emissions AND Failure of 15% moisture content of tailings | None | Transboundary contamination of ground water
Handling - transport of tailings could cause dust emissions AND Failure of 15% moisture content of tailings | None | Transboundary contamination of air water
Handling - transport of tailings could cause dust emissions AND Failure of 15% moisture content of tailings | None | Occupational health risk
Handling - transport of tailings could cause dust emissions AND Failure of Dry stack design - management - freezing | None | Transboundary contamination of surface water
Handling - transport of tailings could cause dust emissions AND Failure of Dry stack design - management - freezing | None | Transboundary contamination of ground water
Handling - transport of tailings could cause dust emissions AND Failure of Dry stack design - management - freezing | None | Transboundary contamination of air water
Handling - transport of tailings could cause dust emissions AND Failure of Management of fugitive dust during summer months | None | Transboundary contamination of surface water
Handling - transport of tailings could cause dust emissions AND Failure of Management of fugitive dust during summer months | None | Transboundary contamination of ground water
Handling - transport of tailings could cause dust emissions AND Failure of Management of fugitive dust during summer months | None | Transboundary contamination of air water
Handling - transport of tailings could cause dust emissions AND Failure of Management of fugitive dust during summer months | None | Management of fugitive dust during summer months
Handling - transport of tailings could cause dust emissions | Improper handling procedures AND Failure of Worker training | None
Handling - transport of tailings could cause dust emissions | Failure of covers on trucks AND Failure of Worker training | None
Handling - transport of tailings could cause dust emissions | Improper handling procedures AND Failure of Site supervision | None
Handling - transport of tailings could cause dust emissions | Failure of covers on trucks AND Failure of Site supervision | None
Handling - transport of tailings could cause dust emissions | Improper handling procedures AND Failure of Occupational Health - Safety Management Plan | None
Handling - transport of tailings could cause dust emissions | Failure of covers on trucks AND Failure of Occupational Health - Safety Management Plan | None
Handling - transport of tailings could cause dust emissions AND Failure of Occupational Health - Safety Management Plan | None | Occupational health risk
Failure of water management system could result in untreated contact water to enter Itchen Lake AND Failure of Visual Inspection of water management system | None | Transboundary contamination of surface water
Failure of water management system could result in untreated contact water to enter Itchen Lake AND Failure of Sampling of water management system | None | Contamination - adverse effects on fish - fish habitat
Failure of water management system could result in untreated contact water to enter Itchen Lake | Failure of tailings storage facility AND Failure of Maintenance of water management system | None
Failure of water management system could result in untreated contact water to enter Itchen Lake AND Failure of Maintenance of water management system | None | Transboundary contamination of surface water
Failure of water management system could result in untreated contact water to enter Itchen Lake AND Failure of Maintenance of water management system | None | Contamination - adverse effects on fish - fish habitat
Failure of water management system could result in untreated contact water to enter Itchen Lake | Thawing/settlement of permafrost leading to dam seepage - failure AND Failure of Geotechnical inspection of the dams | None
Failure of water management system could result in untreated contact water to enter Itchen Lake | Failure of tailings storage facility AND Failure of Geotechnical inspection of the dams | None
Failure of water management system could result in untreated contact water to enter Itchen Lake | Thawing/settlement of permafrost leading to dam seepage - failure AND Failure of Mineral Waste Management Plan | None
Failure of water management system could result in untreated contact water to enter Itchen Lake | Inadequate design capacity AND Failure of Mineral Waste Management Plan | None
Failure of water management system could result in untreated contact water to enter Itchen Lake | Failure of PAG dump AND Failure of Mineral Waste Management Plan | None
Failure of water management system could result in untreated contact water to enter Itchen Lake | Failure of tailings storage facility AND Failure of Mineral Waste Management Plan | None
Failure of water management system could result in untreated contact water to enter Itchen Lake | Thawing/settlement of permafrost leading to dam seepage - failure AND Failure of Waste Water Management Plan | None
Failure of water management system could result in untreated contact water to enter Itchen Lake | Inadequate design capacity AND Failure of Waste Water Management Plan | None
Failure of water management system could result in untreated contact water to enter Itchen Lake | Failure of tailings storage facility AND Failure of Waste Water Management Plan | None
Ground instability could cause failure at the toe of the PAG dump leading to displacement of the PAG load | High loading rate AND Failure of Signoff - approval of proper design - drainage, stabilization of toe, foundation prepping | None
Ground instability could cause failure at the toe of the PAG dump leading to displacement of the PAG load | Steep topography AND Failure of Signoff - approval of proper design - drainage, stabilization of toe, foundation prepping | None
Ground instability could cause failure at the toe of the PAG dump leading to displacement of the PAG load AND Failure of Signoff - approval of proper design - drainage, stabilization of toe, foundation prepping | None | Regulatory non-compliance
Ground instability could cause failure at the toe of the PAG dump leading to displacement of the PAG load AND Failure of Signoff - approval of proper design - drainage, stabilization of toe, foundation prepping | None | Non-compliance with MMG Sustainability Standards
Ground instability could cause failure at the toe of the PAG dump leading to displacement of the PAG load | High loading rate AND Failure of Barriers - berms | None
Ground instability could cause failure at the toe of the PAG dump leading to displacement of the PAG load | Steep topography AND Failure of Barriers - berms | None
Ground instability could cause failure at the toe of the PAG dump leading to displacement of the PAG load AND Failure of Barriers - berms | None | Failure of Water Conveyence System leading to adverse effects on surface water quality
Ground instability could cause failure at the toe of the PAG dump leading to displacement of the PAG load AND Failure of Barriers - berms | None | Failure of Water Conveyence System leading to adverse effects on fish - fish habitat
Ground instability could cause failure at the toe of the PAG dump leading to displacement of the PAG load AND Failure of Barriers - berms | None | Increase cost for remedial work
Ground instability could cause failure at the toe of the PAG dump leading to displacement of the PAG load | Thawing/settlement of permafrost AND Failure of Physical stability monitoring | None
Ground instability could cause failure at the toe of the PAG dump leading to displacement of the PAG load | Insufficient geotechnical information AND Failure of Physical stability monitoring | None
Ground instability could cause failure at the toe of the PAG dump leading to displacement of the PAG load AND Mineral Waste Management Plan | None | Increase cost for remedial work
Ground instability could cause failure at the toe of the PAG dump leading to displacement of the PAG load AND Mineral Waste Management Plan | None | Regulatory non-compliance
Ground instability could cause failure at the toe of the PAG dump leading to displacement of the PAG load AND Mineral Waste Management Plan | None | Non-compliance with MMG Sustainability Standards
Subaqueous cover of PAG waste is not maintained during dry years, leading to exposure of PAG - ARD production during closure | Uncertainty about long-term climate AND Failure of Detailed site-wide water balance - minimum water cover calculated based on evaporation rates during prolonged dry periods | None
Subaqueous cover of PAG waste is not maintained during dry years, leading to exposure of PAG - ARD production during closure | Incorrect water balance AND Failure of Detailed site-wide water balance - minimum water cover calculated based on evaporation rates during prolonged dry periods | None
Subaqueous cover of PAG waste is not maintained during dry years, leading to exposure of PAG - ARD production during closure AND Failure of Detailed site-wide water balance - minimum water cover calculated based on evaporation rates during prolonged dry periods | None | Contamination of surface waters
Subaqueous cover of PAG waste is not maintained during dry years, leading to exposure of PAG - ARD production during closure AND Failure of Detailed site-wide water balance - minimum water cover calculated based on evaporation rates during prolonged dry periods | None | Transboundary contamination of ground water
Subaqueous cover of PAG waste is not maintained during dry years, leading to exposure of PAG - ARD production during closure AND Failure of Detailed site-wide water balance - minimum water cover calculated based on evaporation rates during prolonged dry periods | None | Regulatory non-compliance
Subaqueous cover of PAG waste is not maintained during dry years, leading to exposure of PAG - ARD production during closure AND Failure of Detailed site-wide water balance - minimum water cover calculated based on evaporation rates during prolonged dry periods | None | Deterioration in relationship with regulator
Use of Izok Road by Project vehicles could disrupt/delay calving - post- calving by Bathurst caribou herd | Dramatic declines in Bathurst herd numbers AND Failure of Short-term closure of Izok Road during peak calving period | None
Use of Izok Road by Project vehicles could disrupt/delay calving - post- calving by Bathurst caribou herd | Bathurst herd important to NWT First Nations for food securit AND Failure of Short-term closure of Izok Road during peak calving period | None
Use of Izok Road by Project vehicles could disrupt/delay calving - post- calving by Bathurst caribou herd | None | Lack of social license
Use of Izok Road by Project vehicles could disrupt/delay calving - post- calving by Bathurst caribou herd | None | Reduced herd productivity/mortality
Use of Izok Road by Project vehicles could disrupt/delay calving - post- calving by Bathurst caribou herd | Bathurst herd important to NWT First Nations for food security AND Failure of Adherence to - mobile caribou protection measures | None
Use of Izok Road by Project vehicles could disrupt/delay calving - post- calving by Bathurst caribou herd | Dramatic declines in Bathurst herd numbers AND Failure of Adherence to - mobile caribou protection measures | None
Use of Izok Road by Project vehicles could disrupt/delay calving - post- calving by Bathurst caribou herd | Infringement of Aboriginal rights AND Failure of Adherence to - mobile caribou protection measures | None
Use of Izok Road by Project vehicles could disrupt/delay calving - post- calving by Bathurst caribou herd AND Failure of Adherence to - mobile caribou protection measures | None | Dramatic declines in Bathurst herd numbers
Use of Izok Road by Project vehicles could disrupt/delay calving - post- calving by Bathurst caribou herd AND Failure of Adherence to - mobile caribou protection measures | None | Infringement of Aboriginal rights
Use of Izok Road by Project vehicles could disrupt/delay calving - post- calving by Bathurst caribou herd AND Failure of Adherence to - mobile caribou protection measures | None | Regulatory non-compliance
Use of Izok Road by Project vehicles could disrupt/delay calving - post- calving by Bathurst caribou herd AND Failure of Adherence to - mobile caribou protection measures | None | Non-compliance with MMG Sustainability Standards
Use of Izok Road by Project vehicles could disrupt/delay calving - post- calving by Bathurst caribou herd | Road alignment crosses through prime calving - postcalving grounds of Bathurst herd AND Failure of Road design considerations to facilitate caribou movement - side slopes, road width, slope surface, crossing lengths | None
Use of Izok Road by Project vehicles could disrupt/delay calving - post- calving by Bathurst caribou herd AND Failure of Road design considerations to facilitate caribou movement - side slopes, road width, slope surface, crossing lengths | None | Reduced herd productivity/mortality
Use of Izok Road by Project vehicles could disrupt/delay calving - post- calving by Bathurst caribou herd AND Failure of Road design considerations to facilitate caribou movement - side slopes, road width, slope surface, crossing lengths | None | Lack of social license
Use of Izok Road by Project vehicles could disrupt/delay calving - post- calving by Bathurst caribou herd | Delay in Project approvals schedule AND Re-alignment of road to avoid areas of peak calving - optimum road route | None
Use of Izok Road by Project vehicles could disrupt/delay calving - post- calving by Bathurst caribou herd | More restrictive mitigation measures that are infeasible AND Re-alignment of road to avoid areas of peak calving - optimum road route | None
Use of Izok Road by Project vehicles could disrupt/delay calving - post- calving by Bathurst caribou herd | Accomodation - compensation to NWT First Nations for loss of harvest /harvest opportunities AND Re-alignment of road to avoid areas of peak calving - optimum road route | None
Use of Izok Road by Project vehicles could disrupt/delay calving - post- calving by Bathurst caribou herd | None | Lack of social license
Use of Izok Road by Project vehicles could disrupt/delay calving - post- calving by Bathurst caribou herd AND Re-alignment of road to avoid areas of peak calving - optimum road route | None | Reduced herd productivity/mortality
Use of Izok Road by Project vehicles could disrupt/delay calving - post- calving by Bathurst caribou herd | Road alignment crosses through prime calving - postcalving grounds of Bathurst herd AND Failure of Caribou Monitoring Plan | None
Use of Izok Road by Project vehicles could disrupt/delay calving - post- calving by Bathurst caribou herd | Dramatic declines in Bathurst herd numbers AND Failure of Caribou Monitoring Plan | None
Use of Izok Road by Project vehicles could disrupt/delay calving - post- calving by Bathurst caribou herd AND Failure of Caribou Monitoring Plan | None | Reduced herd productivity/mortality
Use of Izok Road by Project vehicles could disrupt/delay calving - post- calving by Bathurst caribou herd | Dramatic declines in Bathurst herd numbers AND Failure of Caribou Mitigation Plan | None
Use of Izok Road by Project vehicles could disrupt/delay calving - post- calving by Bathurst caribou herd AND Failure of Caribou Mitigation Plan | None | Compensation to NWT First Nations for lost harvest -/- harvest oppurtunities
Use of Izok Road by Project vehicles could disrupt/delay calving - post- calving by Bathurst caribou herd AND Failure of Caribou Mitigation Plan | None | Lack of social license
Use of Izok Road by Project vehicles could disrupt/delay calving - post- calving by Bathurst caribou herd AND Failure of Caribou Mitigation Plan | None | Reduced herd productivity/mortality
Use of Izok Road by Project vehicles could disrupt/delay calving - post- calving by Bathurst caribou herd | Road alignment crosses through prime calving - postcalving grounds of Bathurst herd AND Failure of Regulatory non-compliance | None
Use of Izok Road by Project vehicles could disrupt/delay calving - post- calving by Bathurst caribou herd | Bathurst herd important to NWT First Nations for food security AND Failure of Adherence to - mobile caribou protection measures | None
Use of Izok Road by Project vehicles could disrupt/delay calving - post- calving by Bathurst caribou herd | Dramatic declines in Bathurst herd numbers AND Failure of Road Management Plan | None
Use of Izok Road by Project vehicles could disrupt/delay calving - post- calving by Bathurst caribou herd AND Failure of Road Management Plan | None | Reduced herd productivity/mortality
Use of Izok Road by Project vehicles could disrupt/delay calving - post- calving by Bathurst caribou herd AND Failure of Communicate about controls effectively to stakeholders | None | Infringement of Aboriginal rights
Potential disturbance of DU caribou herd on wintering grounds - during ice crossings between mainland - Victoria Island from project activities | Early ice freezeup -/- late breakup AND Failure of Shipping window selected based on available - 1987–2006 satellite telemetry data of caribou movements | None
Potential disturbance of DU caribou herd on wintering grounds - during ice crossings between mainland - Victoria Island from project activities AND Failure of Shipping window selected based on available - 1987–2006 satellite telemetry data of caribou movements | None | Restrictions on shipping window
Potential disturbance of DU caribou herd on wintering grounds - during ice crossings between mainland - Victoria Island from project activities | Early ice freezeup -/- late breakup AND Failure of Caribou Monitoring Plan | None
Potential disturbance of DU caribou herd on wintering grounds - during ice crossings between mainland - Victoria Island from project activities AND Failure of Caribou Monitoring Plan | None | Caribou mortality
Potential disturbance of DU caribou herd on wintering grounds - during ice crossings between mainland - Victoria Island from project activities AND Failure of Caribou Monitoring Plan | None | Caribou mortality
Potential disturbance of DU caribou herd on wintering grounds - during ice crossings between mainland - Victoria Island from project activities AND Failure of Caribou Monitoring Plan | None | Accomodation - compensation to Inuvialuit
Potential disturbance of DU caribou herd on wintering grounds - during ice crossings between mainland - Victoria Island from project activities AND Failure of Caribou Monitoring Plan | None | Loss of havest/harvest oppurtunities - Holman Island
Potential disturbance of DU caribou herd on wintering grounds - during ice crossings between mainland - Victoria Island from project activities AND Failure of Road Management Plan | None | Caribou mortality
Potential disturbance of DU caribou herd on wintering grounds - during ice crossings between mainland - Victoria Island from project activities | Infringement of Aboriginal rights AND Failure of Communicate about controls effectively to stakeholders | None
Potential disturbance of DU caribou herd on wintering grounds - during ice crossings between mainland - Victoria Island from project activities AND Failure of Communicate about controls effectively to stakeholders | None | Regulatory non-compliance
Potential disturbance of DU caribou herd on wintering grounds - during ice crossings between mainland - Victoria Island from project activities | Early ice freezeup -/- late breakup AND Failure of Calculations for rate of freezeup | None
Potential disturbance of DU caribou herd on wintering grounds - during ice crossings between mainland - Victoria Island from project activities | Ice movement into Coronation Gulf during shipping season AND Failure of Calculations for rate of freezeup | None
Potential disturbance of DU caribou herd on wintering grounds - during ice crossings between mainland - Victoria Island from project activities AND Failure of Calculations for rate of freezeup | None | Restrictions on shipping window
Breaking - management of ice for ship navigation could disrupt spring - fall inter-island movements by Peary caribou AND Failure of Caribou Monitoring Plan | None | Caribou mortality
Breaking - management of ice for ship navigation could disrupt spring - fall inter-island movements by Peary caribou AND Failure of Caribou Monitoring Plan | None | Restrictions on shipping
Breaking - management of ice for ship navigation could disrupt spring - fall inter-island movements by Peary caribou AND Failure of Caribou Monitoring Plan | None | Caribou mortality
Breaking - management of ice for ship navigation could disrupt spring - fall inter-island movements by Peary caribou | Limited information on spring - fall migration dates between island complexes AND Failure of Caribou Mitigation Plan | None
Breaking - management of ice for ship navigation could disrupt spring - fall inter-island movements by Peary caribou AND Failure of Caribou Mitigation Plan | None | Caribou mortality
Breaking - management of ice for ship navigation could disrupt spring - fall inter-island movements by Peary caribou AND Failure of Caribou Mitigation Plan | None | Restrictions on shipping
Breaking - management of ice for ship navigation could disrupt spring - fall inter-island movements by Peary caribou | Limited information on spring - fall migration dates between island complexes AND Failure of Onboard wildlife monitoring | None
Breaking - management of ice for ship navigation could disrupt spring - fall inter-island movements by Peary caribou AND Failure of Onboard wildlife monitoring | None | Caribou mortality
Breaking - management of ice for ship navigation could disrupt spring - fall inter-island movements by Peary caribou AND Failure of Onboard wildlife monitoring | None | Restrictions on shipping
Shipping along western route through Alaskan waters could disrupt Alaskan bowhead whale hunt in fall | Infringement of Aboriginal rights AND Failure of Adhere to any shipping restrictions to avoid conflict with harvest | None
Shipping along western route through Alaskan waters could disrupt Alaskan bowhead whale hunt in fall AND Failure of Adhere to any shipping restrictions to avoid conflict with harvest | None | Compensation to NWT First Nations for lost harvest -/- harvest oppurtunities
Ground waters - surface waters are linked through open taliks, which could lead to transport of contaminants to Iznogoudh - Itchen lakes | Flooding of open pits by groundwater - surface water inflows at closure - post-closure AND Failure of Ground freezing to control any large persistent inflow to the mines | None
Ground waters - surface waters are linked through open taliks, which could lead to transport of contaminants to Iznogoudh - Itchen lakes | Infiltration of precipitation through waste rock - tailings dry stack will produce leachate that will report to both the shallow groundwater system underlying the piles - the lake talik beneath Izok Lake AND Failure of Ground freezing to control any large persistent inflow to the mines | None
Ground waters - surface waters are linked through open taliks, which could lead to transport of contaminants to Iznogoudh - Itchen lakes AND Failure of Ground freezing to control any large persistent inflow to the mines | None | Transboundary contamination of ground water
Ground waters - surface waters are linked through open taliks, which could lead to transport of contaminants to Iznogoudh - Itchen lakes AND Failure of Ground freezing to control any large persistent inflow to the mines | None | Fines - penalties for non-compliance with water license
Ground waters - surface waters are linked through open taliks, which could lead to transport of contaminants to Iznogoudh - Itchen lakes AND Failure of Ground freezing to control any large persistent inflow to the mines | None | Non-compliance with MMG Sustainability Standards
Ground waters - surface waters are linked through open taliks, which could lead to transport of contaminants to Iznogoudh - Itchen lakes | Flooding of open pits by groundwater - surface water inflows at closure - post-closure AND Failure of Installation of covers to minimize volume of water that interacts with waste rock - tailings | None
Ground waters - surface waters are linked through open taliks, which could lead to transport of contaminants to Iznogoudh - Itchen lakes | Infiltration of precipitation through waste rock - tailings dry stack will produce leachate that will report to both the shallow groundwater system underlying the piles - the lake talik beneath Izok Lake AND Failure of Installation of covers to minimize volume of water that interacts with waste rock - tailings | None
Ground waters - surface waters are linked through open taliks, which could lead to transport of contaminants to Iznogoudh - Itchen lakes AND Failure of Installation of covers to minimize volume of water that interacts with waste rock - tailings | None | Contamination of surface waters
Ground waters - surface waters are linked through open taliks, which could lead to transport of contaminants to Iznogoudh - Itchen lakes AND Failure of Installation of covers to minimize volume of water that interacts with waste rock - tailings | None | Fines - penalties for non-compliance with water license
Ground waters - surface waters are linked through open taliks, which could lead to transport of contaminants to Iznogoudh - Itchen lakes AND Failure of Installation of covers to minimize volume of water that interacts with waste rock - tailings | None | Non-compliance with MMG Sustainability Standards
Ground waters - surface waters are linked through open taliks, which could lead to transport of contaminants to Iznogoudh - Itchen lakes AND Failure of Permafrost aggradation into waste rock piles - tailings dry stack | None | Transboundary contamination of ground water
Ground waters - surface waters are linked through open taliks, which could lead to transport of contaminants to Iznogoudh - Itchen lakes AND Failure of Permafrost aggradation into waste rock piles - tailings dry stack | None | Fines - penalties for non-compliance with water license
Ground waters - surface waters are linked through open taliks, which could lead to transport of contaminants to Iznogoudh - Itchen lakes AND Failure of Permafrost aggradation into waste rock piles - tailings dry stack | None | Non-compliance with MMG Sustainability Standards
Ground waters - surface waters are linked through open taliks, which could lead to transport of contaminants to Iznogoudh - Itchen lakes | Flooding of open pits by groundwater - surface water inflows at closure - post-closure AND Failure of Correct Site Water Balance | None
Ground waters - surface waters are linked through open taliks, which could lead to transport of contaminants to Iznogoudh - Itchen lakes | Infiltration of precipitation through waste rock - tailings dry stack will produce leachate that will report to both the shallow groundwater system underlying the piles - the lake talik beneath Izok Lake AND Failure of Correct Site Water Balance | None
Ground waters - surface waters are linked through open taliks, which could lead to transport of contaminants to Iznogoudh - Itchen lakes AND Failure of Correct Site Water Balance | None | Fines - penalties for non-compliance with water license
Ground waters - surface waters are linked through open taliks, which could lead to transport of contaminants to Iznogoudh - Itchen lakes AND Failure of Correct Site Water Balance | None | Non-compliance with MMG Sustainability Standards
Disruption - destruction of migratory birds, nests - eggs in - around construction areas - project infrastructure would result in contravention of the Migratory Birds Convention Act | Failure to adhere to Beneficial Management Practices - e.g, appropriate timing windows AND Failure of Monitoring | None
Disruption - destruction of migratory birds, nests - eggs in - around construction areas - project infrastructure would result in contravention of the Migratory Birds Convention Act AND Failure of Monitoring | None | Fines - penalties for MBCA violations
Disruption - destruction of migratory birds, nests - eggs in - around construction areas - project infrastructure would result in contravention of the Migratory Birds Convention Act AND Failure of Monitoring | None | Deterioration in relationship with regulator
Disruption - destruction of migratory birds, nests - eggs in - around construction areas - project infrastructure would result in contravention of the Migratory Birds Convention Act AND Failure of Monitoring | None | Non-compliance with MMG Sustainability Standards
Disruption - destruction of migratory birds, nests - eggs in - around construction areas - project infrastructure would result in contravention of the Migratory Birds Convention Act | Failure to adhere to Beneficial Management Practices - e.g, appropriate timing windows AND Failure of Nest-specific management plans | None
Disruption - destruction of migratory birds, nests - eggs in - around construction areas - project infrastructure would result in contravention of the Migratory Birds Convention Act | Failure to undertake non-intrusive monitoring for nesting AND Failure of Nest-specific management plans | None
Disruption - destruction of migratory birds, nests - eggs in - around construction areas - project infrastructure would result in contravention of the Migratory Birds Convention Act | Failure to adhere to Beneficial Management Practices - e.g, appropriate timing windows AND Failure of Construction windows | None
Disruption - destruction of migratory birds, nests - eggs in - around construction areas - project infrastructure would result in contravention of the Migratory Birds Convention Act | Poor communication between Environmental personnel - construction/operations crew AND Failure of Construction windows | None
Disruption - destruction of migratory birds, nests - eggs in - around construction areas - project infrastructure would result in contravention of the Migratory Birds Convention Act AND Failure of Construction windows | None | Fines - penalties for MBCA violations
Disruption - destruction of migratory birds, nests - eggs in - around construction areas - project infrastructure would result in contravention of the Migratory Birds Convention Act AND Failure of Construction windows | None | Deterioration in relationship with regulator
Disruption - destruction of migratory birds, nests - eggs in - around construction areas - project infrastructure would result in contravention of the Migratory Birds Convention Act AND Failure of Construction windows | None | Non-compliance with MMG Sustainability Standards
Disruption - destruction of migratory birds, nests - eggs in - around construction areas - project infrastructure would result in contravention of the Migratory Birds Convention Act | Failure to adhere to Beneficial Management Practices - e.g, appropriate timing windows AND Failure of Avoidance of nesting areas | None
Disruption - destruction of migratory birds, nests - eggs in - around construction areas - project infrastructure would result in contravention of the Migratory Birds Convention Act | Poor communication between Environmental personnel - construction/operations crew AND Failure of Avoidance of nesting areas | None
Disruption - destruction of migratory birds, nests - eggs in - around construction areas - project infrastructure would result in contravention of the Migratory Birds Convention Act AND Failure of Avoidance of nesting areas | None | Fines - penalties for MBCA violations
Disruption - destruction of migratory birds, nests - eggs in - around construction areas - project infrastructure would result in contravention of the Migratory Birds Convention Act AND Failure of Avoidance of nesting areas | None | Deterioration in relationship with regulator
Disruption - destruction of migratory birds, nests - eggs in - around construction areas - project infrastructure would result in contravention of the Migratory Birds Convention Act AND Failure of Avoidance of nesting areas | None | Non-compliance with MMG Sustainability Standards
Disruption - destruction of migratory birds, nests - eggs in - around construction areas - project infrastructure would result in contravention of the Migratory Birds Convention Act | Failure to adhere to Beneficial Management Practices - e.g, appropriate timing windows AND Failure of Deterrant measures to prevent nesting on Project infrastructure | None
Disruption - destruction of migratory birds, nests - eggs in - around construction areas - project infrastructure would result in contravention of the Migratory Birds Convention Act AND Failure of Deterrant measures to prevent nesting on Project infrastructure | None | Fines - penalties for MBCA violations
Disruption - destruction of migratory birds, nests - eggs in - around construction areas - project infrastructure would result in contravention of the Migratory Birds Convention Act AND Failure of Deterrant measures to prevent nesting on Project infrastructure | None | Delay in construction
Disruption - destruction of migratory birds, nests - eggs in - around construction areas - project infrastructure would result in contravention of the Migratory Birds Convention Act AND Failure of Deterrant measures to prevent nesting on Project infrastructure | None | Delay in operations
Presence of wildlife in the Project area could delay construction - operation activities - lead to human-wildlife interactions | Poor waste management practices AND Failure of Non-mineral Waste Management Plan | None
Presence of wildlife in the Project area could delay construction - operation activities - lead to human-wildlife interactions AND Failure of Non-mineral Waste Management Plan | None | Delay in operations
Presence of wildlife in the Project area could delay construction - operation activities - lead to human-wildlife interactions AND Failure of Non-mineral Waste Management Plan | None | Injuries/fatalities
Presence of wildlife in the Project area could delay construction - operation activities - lead to human-wildlife interactions | Attraction to lighting on Project infrastructure AND Failure of Proper lighting design on Project infrastructure to minimize wildlife attraction | None
Presence of wildlife in the Project area could delay construction - operation activities - lead to human-wildlife interactions | Presence of Project infrastructure in wildlife territory/seasonal ranges/migratory paths AND Failure of Proper lighting design on Project infrastructure to minimize wildlife attraction | None
Presence of wildlife in the Project area could delay construction - operation activities - lead to human-wildlife interactions AND Failure of Proper lighting design on Project infrastructure to minimize wildlife attraction | None | Delay in operations
Presence of wildlife in the Project area could delay construction - operation activities - lead to human-wildlife interactions AND Failure of Proper lighting design on Project infrastructure to minimize wildlife attraction | None | Injuries/fatalities
Presence of wildlife in the Project area could delay construction - operation activities - lead to human-wildlife interactions | Poor waste management practices AND Failure of Comprehensive wildlife baseline programs | None
Presence of wildlife in the Project area could delay construction - operation activities - lead to human-wildlife interactions | Attraction to lighting on Project infrastructure AND Failure of Comprehensive wildlife baseline programs | None
Presence of wildlife in the Project area could delay construction - operation activities - lead to human-wildlife interactions | Presence of Project infrastructure in wildlife territory/seasonal ranges/migratory paths AND Failure of Comprehensive wildlife baseline programs | None
Presence of wildlife in the Project area could delay construction - operation activities - lead to human-wildlife interactions AND Failure of Comprehensive wildlife baseline programs | None | Delay in operations
Presence of wildlife in the Project area could delay construction - operation activities - lead to human-wildlife interactions AND Failure of Comprehensive wildlife baseline programs | None | Need to destroy nuisance wildlife
Presence of wildlife in the Project area could delay construction - operation activities - lead to human-wildlife interactions AND Failure of Comprehensive wildlife baseline programs | None | Injuries/fatalities
Presence of wildlife in the Project area could delay construction - operation activities - lead to human-wildlife interactions AND Failure of Wildlife monitoring | None | Injuries/fatalities
Presence of wildlife in the Project area could delay construction - operation activities - lead to human-wildlife interactions AND Failure of Wildlife monitoring | None | Delay in operations
Presence of wildlife in the Project area could delay construction - operation activities - lead to human-wildlife interactions AND Failure of Wildlife monitoring | None | Need to destroy nuisance wildlife
Presence of wildlife in the Project area could delay construction - operation activities - lead to human-wildlife interactions AND Failure of Wildlife training | None | Need to destroy nuisance wildlife
Presence of wildlife in the Project area could delay construction - operation activities - lead to human-wildlife interactions AND Failure of Wildlife training | None | Injuries/fatalities
Inflated closure - reclamation costs | Lack of comprehensive baseline environmental data AND Failure of Comprehensive environmental baseline programs | None
Inflated closure - reclamation costs | Incorrect water balance AND Failure of Comprehensive environmental baseline programs | None
Inflated closure - reclamation costs AND Failure of Comprehensive environmental baseline programs | None | Requirement for increased financial assurances
Inflated closure - reclamation costs AND Failure of Comprehensive environmental baseline programs | None | Delay in permitting schedule
Inflated closure - reclamation costs AND Failure of Comprehensive environmental baseline programs | None | Regulatory non-compliance
Inflated closure - reclamation costs AND Failure of Comprehensive environmental baseline programs | None | Non-compliance with MMG Sustainability Standards
Inflated closure - reclamation costs AND Failure of Comprehensive environmental baseline programs | None | Increased liability risk - fines - penalties
Inflated closure - reclamation costs AND Failure of Comprehensive environmental baseline programs | None | Increased closure costs - schedule
Inflated closure - reclamation costs AND Failure of Comprehensive environmental baseline programs | None | Loss of reclamation bonding
Inflated closure - reclamation costs | Lack of stakeholder participation AND Failure of takeholder consulation program, including TK/IQ programs with Kitikmeot communities | None
Inflated closure - reclamation costs AND Failure of takeholder consulation program, including TK/IQ programs with Kitikmeot communities | None | Requirement for increased financial assurances
Inflated closure - reclamation costs AND Failure of takeholder consulation program, including TK/IQ programs with Kitikmeot communities | None | Reputational damage
Cost cutting measures during road construction could result in insufficient robustness, durability - suitability of road design - compromise reliability - safety | Poor visibility due to narrow road width, steep gradients - obscured curves AND Failure of Signoff - approval on design | None
Cost cutting measures during road construction could result in insufficient robustness, durability - suitability of road design - compromise reliability - safety AND Failure of Signoff - approval on design | None | Vehicular collisions causing injuries/fatalities
Cost cutting measures during road construction could result in insufficient robustness, durability - suitability of road design - compromise reliability - safety AND Failure of Signoff - approval on design | None | Wildlife collision
Cost cutting measures during road construction could result in insufficient robustness, durability - suitability of road design - compromise reliability - safety AND Failure of Signoff - approval on design | None | Inadequate erosion control
Cost cutting measures during road construction could result in insufficient robustness, durability - suitability of road design - compromise reliability - safety AND Failure of Signoff - approval on design | None | Bridge failure leading to road closure
Cost cutting measures during road construction could result in insufficient robustness, durability - suitability of road design - compromise reliability - safety AND Failure of Road Management Plan | None | Vehicular collisions causing injuries/fatalities
Cost cutting measures during road construction could result in insufficient robustness, durability - suitability of road design - compromise reliability - safety AND Failure of Road Management Plan | None | Wildlife collision
Cost cutting measures during road construction could result in insufficient robustness, durability - suitability of road design - compromise reliability - safety AND Failure of Road Management Plan | None | Inadequate erosion control
Cost cutting measures during road construction could result in insufficient robustness, durability - suitability of road design - compromise reliability - safety AND Failure of Spill Response Plan | None | Ground Contamination
Cost cutting measures during road construction could result in insufficient robustness, durability - suitability of road design - compromise reliability - safety AND Failure of Spill Response Plan | None | Transboundary contamination of ground water
Handling - transport of concentrate could result of loss of product through dust generation - small spills | Improper handling procedures AND Failure of Worker training | None
Handling - transport of concentrate could result of loss of product through dust generation - small spills | Inability to meet - maintain target moisture level AND Failure of Worker training | None
Handling - transport of concentrate could result of loss of product through dust generation - small spills | Improper handling procedures AND Failure of Site supervision | None
Handling - transport of concentrate could result of loss of product through dust generation - small spills | Failure of covers on trucks AND Failure of Site supervision | None
Handling - transport of concentrate could result of loss of product through dust generation - small spills | Failure of covers on conveyers AND Failure of Site supervision | None
Handling - transport of concentrate could result of loss of product through dust generation - small spills | Lack of dust collectors in storage shed - concentrator AND Failure of Site supervision | None
Handling - transport of concentrate could result of loss of product through dust generation - small spills | Inability to meet - maintain target moisture level AND Failure of Site supervision AND Failure of Equipment Inspection - Maintenance | None
Handling - transport of concentrate could result of loss of product through dust generation - small spills | Failure of covers on trucks AND Failure of Equipment Inspection - Maintenance | None
Handling - transport of concentrate could result of loss of product through dust generation - small spills | Failure of covers on conveyers AND Failure of Equipment Inspection - Maintenance | None
Handling - transport of concentrate could result of loss of product through dust generation - small spills | Lack of dust collectors in storage shed - concentrator AND Failure of Equipment Inspection - Maintenance | None
Handling - transport of concentrate could result of loss of product through dust generation - small spills AND Failure of Equipment Inspection - Maintenance | None | Ground Contamination
Handling - transport of concentrate could result of loss of product through dust generation - small spills AND Failure of Equipment Inspection - Maintenance | None | Transboundary contamination of ground water
Handling - transport of concentrate could result of loss of product through dust generation - small spills AND Failure of Equipment Inspection - Maintenance | None | Occupational health risk
Transport of contaminants into the Kennarctic River due to connectivity with High Lake through open talik could lead to a reduction in water quality | Open talik AND Failure of Hydrogeology drillings in High Lake to determine type of talk | None
Transport of contaminants into the Kennarctic River due to connectivity with High Lake through open talik could lead to a reduction in water quality | Exposure of PAG AND Failure of Subaqueous cover of PAG to minimize oxidation | None
Potential disturbance of Project shipping on marine mammals - harvest | Inadequate consultation within transboundary community - regulators AND Failure of Consultation strategy includes meetings with communities along the western shipping routes - Inuvialuit Settlement Region, as well as NWT regulators | None
Potential disturbance of Project shipping on marine mammals - harvest AND Failure of Consultation strategy includes meetings with communities along the western shipping routes - Inuvialuit Settlement Region, as well as NWT regulators | None | Infringement of Aboriginal rights
Potential disturbance of Project shipping on marine mammals - harvest AND Failure of Consultation strategy includes meetings with communities along the western shipping routes - Inuvialuit Settlement Region, as well as NWT regulators | None | Infrigement of aboriginal accomodation.
Potential disturbance of Project shipping on marine mammals - harvest AND Failure of Shipping Management Plan | None | Infringement of Aboriginal rights
Potential disturbance of Project shipping on marine mammals - harvest AND Failure of Shipping Management Plan | None | Restrictions on shipping
Potential disturbance of Project shipping on marine mammals - harvest AND Failure of Adherence to ISR Beluga Management Plans | None | Infringement of Aboriginal rights
Significant release of fuel, reagents - concentrate could occur at the port leading to water contamination AND Failure of Spill Response Training | None | Environmental damage
Significant release of fuel, reagents - concentrate could occur at the port leading to water contamination AND Failure of Spill Response Training | None | Reputational damage
Significant release of fuel, reagents - concentrate could occur at the port leading to water contamination AND Failure of Spill Response Training | None | Cost of cleanup
Significant release of fuel, reagents - concentrate could occur at the port leading to water contamination AND Failure of Spill Response Training | None | Cost of compensation
Significant release of fuel, reagents - concentrate could occur at the port leading to water contamination AND Failure of Spill Response Training | None | Fines - penalties
Significant release of fuel, reagents - concentrate could occur at the port leading to water contamination AND Failure of Spill Response Training | None | Delay in Operations
Significant release of fuel, reagents - concentrate could occur at the port leading to water contamination AND Failure of Spill Contingency - Emergency Response plans | None | Environmental damage
Significant release of fuel, reagents - concentrate could occur at the port leading to water contamination AND Failure of Spill Contingency - Emergency Response plans | None | Reputational damage
Significant release of fuel, reagents - concentrate could occur at the port leading to water contamination AND Failure of Spill Contingency - Emergency Response plans | None | Cost of cleanup
Significant release of fuel, reagents - concentrate could occur at the port leading to water contamination AND Failure of Spill Contingency - Emergency Response plans | None | Cost of compensation
Significant release of fuel, reagents - concentrate could occur at the port leading to water contamination AND Failure of Spill Contingency - Emergency Response plans | None | Fines - penalties
Significant release of fuel, reagents - concentrate could occur at the port leading to water contamination AND Failure of Spill Contingency - Emergency Response plans | None | Delay in Operations
Significant release of fuel, reagents - concentrate could occur at the port leading to water contamination AND Failure of Spill Equipment | None | Environmental damage
Significant release of fuel, reagents - concentrate could occur at the port leading to water contamination AND Failure of Spill Equipment | None | Reputational damage
Significant release of fuel, reagents - concentrate could occur at the port leading to water contamination AND Failure of Spill Equipment | None | Cost of cleanup
Significant release of fuel, reagents - concentrate could occur at the port leading to water contamination AND Failure of Spill Equipment | None | Cost of compensation
Significant release of fuel, reagents - concentrate could occur at the port leading to water contamination AND Failure of Spill Equipment | None | Fines - penalties
Significant release of fuel, reagents - concentrate could occur at the port leading to water contamination AND Failure of Spill Equipment | None | Delay in Operations
Significant release of fuel, reagents - concentrate could occur at the port leading to water contamination AND Failure of Response Boat | None | Environmental damage
Significant release of fuel, reagents - concentrate could occur at the port leading to water contamination AND Failure of Response Boat | None | Reputational damage
Significant release of fuel, reagents - concentrate could occur at the port leading to water contamination AND Failure of Response Boat | None | Cost of cleanup
Significant release of fuel, reagents - concentrate could occur at the port leading to water contamination AND Failure of Response Boat | None | Cost of compensation
Significant release of fuel, reagents - concentrate could occur at the port leading to water contamination AND Failure of Response Boat | None | Fines - penalties
Significant release of fuel, reagents - concentrate could occur at the port leading to water contamination AND Failure of Response Boat | None | Delay in Operations
Significant release of fuel, reagents - concentrate could occur at the port leading to water contamination AND Failure of Booming of vessels during loading/ offloading | None | Environmental damage
Significant release of fuel, reagents - concentrate could occur at the port leading to water contamination AND Failure of Booming of vessels during loading/ offloading | None | Reputational damage
Significant release of fuel, reagents - concentrate could occur at the port leading to water contamination AND Failure of Booming of vessels during loading/ offloading | None | Cost of cleanup
Significant release of fuel, reagents - concentrate could occur at the port leading to water contamination AND Failure of Booming of vessels during loading/ offloading | None | Cost of compensation
Significant release of fuel, reagents - concentrate could occur at the port leading to water contamination AND Failure of Booming of vessels during loading/ offloading | None | Fines - penalties
Significant release of fuel, reagents - concentrate could occur at the port leading to water contamination AND Failure of Booming of vessels during loading/ offloading | None | Delay in Operations
Significant release of fuel, reagents - concentrate could occur at the port leading to water contamination AND Failure of Combination of ditches, ponds, - stormwater vaults to collect any concentrate - fuel spill at dock | None | Environmental damage
Significant release of fuel, reagents - concentrate could occur at the port leading to water contamination AND Failure of Combination of ditches, ponds, - stormwater vaults to collect any concentrate - fuel spill at dock | None | Reputational damage
Significant release of fuel, reagents - concentrate could occur at the port leading to water contamination AND Failure of Combination of ditches, ponds, - stormwater vaults to collect any concentrate - fuel spill at dock | None | Cost of cleanup
Significant release of fuel, reagents - concentrate could occur at the port leading to water contamination AND Failure of Combination of ditches, ponds, - stormwater vaults to collect any concentrate - fuel spill at dock | None | Cost of compensation
Significant release of fuel, reagents - concentrate could occur at the port leading to water contamination AND Failure of Combination of ditches, ponds, - stormwater vaults to collect any concentrate - fuel spill at dock | None | Fines - penalties
Significant release of fuel, reagents - concentrate could occur at the port leading to water contamination AND Failure of Combination of ditches, ponds, - stormwater vaults to collect any concentrate - fuel spill at dock | None | Delay in Operations
Significant release of fuel, reagents - concentrate could occur at the port leading to water contamination | Human error AND Failure of Monitoring | None
Significant release of fuel, reagents - concentrate could occur at the port leading to water contamination | Failure of loading/offloading equipment AND Failure of Monitoring | None
Significant release of fuel, reagents - concentrate could occur at the port leading to water contamination | Inclement weather AND Failure of Monitoring | None
Significant release of fuel, reagents - concentrate could occur at the port leading to water contamination | Human error AND Failure of Enclosed concentrate conveyor | None
Significant release of fuel, reagents - concentrate could occur at the port leading to water contamination AND Failure of Enclosed concentrate conveyor | None | Environmental damage
Significant release of fuel, reagents - concentrate could occur at the port leading to water contamination AND Failure of Enclosed concentrate conveyor | None | Reputational damage
Significant release of fuel, reagents - concentrate could occur at the port leading to water contamination AND Failure of Enclosed concentrate conveyor | None | Cost of cleanup
Significant release of fuel, reagents - concentrate could occur at the port leading to water contamination AND Failure of Enclosed concentrate conveyor | None | Cost of compensation
Significant release of fuel, reagents - concentrate could occur at the port leading to water contamination AND Failure of Enclosed concentrate conveyor | None | Fines - penalties
Significant release of fuel, reagents - concentrate could occur at the port leading to water contamination AND Failure of Enclosed concentrate conveyor | None | Delay in Operations
Significant release of fuel, reagents - concentrate could occur at the port leading to water contamination AND Failure of Bermed fuel pipeline | None | Environmental damage
Significant release of fuel, reagents - concentrate could occur at the port leading to water contamination AND Failure of Bermed fuel pipeline | None | Reputational damage
Significant release of fuel, reagents - concentrate could occur at the port leading to water contamination AND Failure of Bermed fuel pipeline | None | Cost of cleanup
Significant release of fuel, reagents - concentrate could occur at the port leading to water contamination AND Failure of Bermed fuel pipeline | None | Cost of compensation
Significant release of fuel, reagents - concentrate could occur at the port leading to water contamination AND Failure of Bermed fuel pipeline | None | Fines - penalties
Significant release of fuel, reagents - concentrate could occur at the port leading to water contamination AND Failure of Bermed fuel pipeline | None | Delay in Operations
Significant release of fuel, reagents - concentrate could occur at the port leading to water contamination AND Failure of Sump/vault system | None | Environmental damage
Significant release of fuel, reagents - concentrate could occur at the port leading to water contamination AND Failure of Sump/vault system | None | Reputational damage
Significant release of fuel, reagents - concentrate could occur at the port leading to water contamination AND Failure of Sump/vault system | None | Cost of cleanup
Significant release of fuel, reagents - concentrate could occur at the port leading to water contamination AND Failure of Sump/vault system | None | Cost of compensation
Significant release of fuel, reagents - concentrate could occur at the port leading to water contamination AND Failure of Sump/vault system | None | Fines - penalties
Significant release of fuel, reagents - concentrate could occur at the port leading to water contamination AND Failure of Sump/vault system | None | Delay in Operations
An accidental involving Project vessels - run aground, collision could cause a significant spill of fuel, reagents - concentrate into marine waters | Failure of navigation system AND Failure of Regular inspection - maintenance of vessel - control systems | None
An accidental involving Project vessels - run aground, collision could cause a significant spill of fuel, reagents - concentrate into marine waters | Loss of power AND Failure of Regular inspection - maintenance of vessel - control systems | None
An accidental involving Project vessels - run aground, collision could cause a significant spill of fuel, reagents - concentrate into marine waters | Explosion/fire AND Failure of Regular inspection - maintenance of vessel - control systems | None
An accidental involving Project vessels - run aground, collision could cause a significant spill of fuel, reagents - concentrate into marine waters | Failure of navigation system AND Failure of Collision Risk Management System - Prevention | None
An accidental involving Project vessels - run aground, collision could cause a significant spill of fuel, reagents - concentrate into marine waters | Inclement weather AND Failure of Collision Risk Management System - Prevention | None
An accidental involving Project vessels - run aground, collision could cause a significant spill of fuel, reagents - concentrate into marine waters | Poor Ice Conditions AND Failure of Collision Risk Management System - Prevention | None
An accidental involving Project vessels - run aground, collision could cause a significant spill of fuel, reagents - concentrate into marine waters | Human error AND Failure of Collision Risk Management System - Prevention | None
An accidental involving Project vessels - run aground, collision could cause a significant spill of fuel, reagents - concentrate into marine waters | Loss of power AND Failure of Collision Risk Management System - Prevention | None
An accidental involving Project vessels - run aground, collision could cause a significant spill of fuel, reagents - concentrate into marine waters | Explosion/fire AND Failure of Collision Risk Management System - Prevention | None
An accidental involving Project vessels - run aground, collision could cause a significant spill of fuel, reagents - concentrate into marine waters | Increase in ship traffic AND Failure of Collision Risk Management System - Prevention | None
An accidental involving Project vessels - run aground, collision could cause a significant spill of fuel, reagents - concentrate into marine waters AND Failure of Collision Risk Management System - Emergency Response | None | Reputational damage
An accidental involving Project vessels - run aground, collision could cause a significant spill of fuel, reagents - concentrate into marine waters AND Failure of Collision Risk Management System - Emergency Response | None | Cost of cleanup
An accidental involving Project vessels - run aground, collision could cause a significant spill of fuel, reagents - concentrate into marine waters AND Failure of Collision Risk Management System - Emergency Response | None | Cost of compensation
An accidental involving Project vessels - run aground, collision could cause a significant spill of fuel, reagents - concentrate into marine waters AND Failure of Collision Risk Management System - Emergency Response | None | Fines - penalties
An accidental involving Project vessels - run aground, collision could cause a significant spill of fuel, reagents - concentrate into marine waters AND Failure of Collision Risk Management System - Emergency Response | None | Delay in operations
An accidental involving Project vessels - run aground, collision could cause a significant spill of fuel, reagents - concentrate into marine waters AND Failure of Collision Risk Management System - Contingency Procedures | None | Environmental damage
An accidental involving Project vessels - run aground, collision could cause a significant spill of fuel, reagents - concentrate into marine waters AND Failure of Collision Risk Management System - Contingency Procedures | None | Reputational damage
An accidental involving Project vessels - run aground, collision could cause a significant spill of fuel, reagents - concentrate into marine waters AND Failure of Collision Risk Management System - Contingency Procedures | None | Cost of cleanup
An accidental involving Project vessels - run aground, collision could cause a significant spill of fuel, reagents - concentrate into marine waters AND Failure of Collision Risk Management System - Contingency Procedures | None | Cost of compensation
An accidental involving Project vessels - run aground, collision could cause a significant spill of fuel, reagents - concentrate into marine waters AND Failure of Collision Risk Management System - Contingency Procedures | None | Fines - penalties
An accidental involving Project vessels - run aground, collision could cause a significant spill of fuel, reagents - concentrate into marine waters AND Failure of Collision Risk Management System - Contingency Procedures | None | Delay in operations
An accidental involving Project vessels - run aground, collision could cause a significant spill of fuel, reagents - concentrate into marine waters AND Failure of Marine Spill Reponse Plan | None | Environmental damage
An accidental involving Project vessels - run aground, collision could cause a significant spill of fuel, reagents - concentrate into marine waters AND Failure of Marine Spill Reponse Plan | None | Reputational damage
An accidental involving Project vessels - run aground, collision could cause a significant spill of fuel, reagents - concentrate into marine waters AND Failure of Marine Spill Reponse Plan | None | Cost of cleanup
An accidental involving Project vessels - run aground, collision could cause a significant spill of fuel, reagents - concentrate into marine waters AND Failure of Marine Spill Reponse Plan | None | Cost of compensation
An accidental involving Project vessels - run aground, collision could cause a significant spill of fuel, reagents - concentrate into marine waters AND Failure of Marine Spill Reponse Plan | None | Fines - penalties
An accidental involving Project vessels - run aground, collision could cause a significant spill of fuel, reagents - concentrate into marine waters AND Failure of Marine Spill Reponse Plan | None | Delay in operations
An accidental involving Project vessels - run aground, collision could cause a significant spill of fuel, reagents - concentrate into marine waters AND Failure of Marine Spill Cleanup Plan Oilspill Atlases | None | Environmental damage
An accidental involving Project vessels - run aground, collision could cause a significant spill of fuel, reagents - concentrate into marine waters AND Failure of Marine Spill Cleanup Plan Oilspill Atlases | None | Reputational damage
An accidental involving Project vessels - run aground, collision could cause a significant spill of fuel, reagents - concentrate into marine waters AND Failure of Marine Spill Cleanup Plan Oilspill Atlases | None | Cost of cleanup
An accidental involving Project vessels - run aground, collision could cause a significant spill of fuel, reagents - concentrate into marine waters AND Failure of Marine Spill Cleanup Plan Oilspill Atlases | None | Cost of compensation
An accidental involving Project vessels - run aground, collision could cause a significant spill of fuel, reagents - concentrate into marine waters AND Failure of Marine Spill Cleanup Plan Oilspill Atlases | None | Fines - penalties
An accidental involving Project vessels - run aground, collision could cause a significant spill of fuel, reagents - concentrate into marine waters AND Failure of Marine Spill Cleanup Plan Oilspill Atlases | None | Delay in operations
An accidental involving Project vessels - run aground, collision could cause a significant spill of fuel, reagents - concentrate into marine waters | Failure of navigation system AND Failure of Bathymetric mapping of shipping corridors | None
Failure of the fuel storage tanks could lead to explosions - ground - water contamination | Vapour ignition - fire AND Failure of Regular tank inspection, maintenance - record keeping | None
Failure of the fuel storage tanks could lead to explosions - ground - water contamination | Structural failure of tank - pipes/valves AND Failure of Regular tank inspection, maintenance - record keeping | None
Failure of the fuel storage tanks could lead to explosions - ground - water contamination | Differential settlement AND Failure of Regular tank inspection, maintenance - record keeping | None
Failure of the fuel storage tanks could lead to explosions - ground - water contamination | Over-pressurization due to faulty instrumentation AND Failure of Regular tank inspection, maintenance - record keeping | None
Failure of the fuel storage tanks could lead to explosions - ground - water contamination | Vapour ignition - fire AND Failure of Adherence to construction standards - codes | None
Failure of the fuel storage tanks could lead to explosions - ground - water contamination | Structural failure of tank - pipes/valves AND Failure of Adherence to construction standards - codes | None
Failure of the fuel storage tanks could lead to explosions - ground - water contamination | Differential settlement AND Failure of Adherence to construction standards - codes | None
Failure of the fuel storage tanks could lead to explosions - ground - water contamination | Human error AND Failure of Adherence to current tank design standards | None
Failure of the fuel storage tanks could lead to explosions - ground - water contamination | Vapour ignition - fire AND Failure of Adherence to current tank design standards | None
Failure of the fuel storage tanks could lead to explosions - ground - water contamination | Structural failure of tank - pipes/valves AND Failure of Adherence to current tank design standards | None
Failure of the fuel storage tanks could lead to explosions - ground - water contamination | Differential settlement AND Failure of Adherence to current tank design standards | None
Failure of the fuel storage tanks could lead to explosions - ground - water contamination | Vapour ignition - fire AND Failure of Low-level alarm indicator | None
Failure of the fuel storage tanks could lead to explosions - ground - water contamination | Lightening strike AND Failure of Low-level alarm indicator | None
Failure of the fuel storage tanks could lead to explosions - ground - water contamination | Over-pressurization due to faulty instrumentation AND Failure of Low-level alarm indicator | None
Failure of the fuel storage tanks could lead to explosions - ground - water contamination AND Failure of Low-level alarm indicator | None | Environmental damage
Failure of the fuel storage tanks could lead to explosions - ground - water contamination AND Failure of Low-level alarm indicator | None | Reputational damage
Failure of the fuel storage tanks could lead to explosions - ground - water contamination AND Failure of Low-level alarm indicator | None | Infrastructure damage
Failure of the fuel storage tanks could lead to explosions - ground - water contamination AND Failure of Low-level alarm indicator | None | Cost of cleanup - repair
Failure of the fuel storage tanks could lead to explosions - ground - water contamination AND Failure of Low-level alarm indicator | None | Fines - penalties for non-compliance
Failure of the fuel storage tanks could lead to explosions - ground - water contamination AND Failure of Low-level alarm indicator | None | Delay in operations
Failure of the fuel storage tanks could lead to explosions - ground - water contamination AND Failure of Low-level alarm indicator | None | Injuries/fatalities
Failure of the fuel storage tanks could lead to explosions - ground - water contamination AND Failure of Secondary containment system | None | Environmental damage
Failure of the fuel storage tanks could lead to explosions - ground - water contamination AND Failure of Secondary containment system | None | Reputational damage
Failure of the fuel storage tanks could lead to explosions - ground - water contamination AND Failure of Secondary containment system | None | Infrastructure damage
Failure of the fuel storage tanks could lead to explosions - ground - water contamination AND Failure of Secondary containment system | None | Cost of cleanup - repair
Failure of the fuel storage tanks could lead to explosions - ground - water contamination AND Failure of Secondary containment system | None | Fines - penalties for non-compliance
Failure of the fuel storage tanks could lead to explosions - ground - water contamination AND Failure of Secondary containment system | None | Delay in operations
Failure of the fuel storage tanks could lead to explosions - ground - water contamination AND Failure of Secondary containment system | None | Injuries/fatalities
An accident involving haul trucks could cause a significant spill of concentrate, fuel - reagent along the road, leading to ground - surface water contamination AND Failure of Spill Contingency - Emergency Response plans | None | Environmental damage
An accident involving haul trucks could cause a significant spill of concentrate, fuel - reagent along the road, leading to ground - surface water contamination AND Failure of Spill Contingency - Emergency Response plans | None | Injuries/fatalities
An accident involving haul trucks could cause a significant spill of concentrate, fuel - reagent along the road, leading to ground - surface water contamination AND Failure of Spill Contingency - Emergency Response plans | None | Reputational damage
An accident involving haul trucks could cause a significant spill of concentrate, fuel - reagent along the road, leading to ground - surface water contamination AND Failure of Spill Contingency - Emergency Response plans | None | Cost of cleanup
An accident involving haul trucks could cause a significant spill of concentrate, fuel - reagent along the road, leading to ground - surface water contamination AND Failure of Spill Contingency - Emergency Response plans | None | Fines - penalties
An accident involving haul trucks could cause a significant spill of concentrate, fuel - reagent along the road, leading to ground - surface water contamination AND Failure of Spill Contingency - Emergency Response plans | None | Non-compliance
An accident involving haul trucks could cause a significant spill of concentrate, fuel - reagent along the road, leading to ground - surface water contamination AND Failure of Spill Contingency - Emergency Response plans | None | Deterioration in relationship with regulator
An accident involving haul trucks could cause a significant spill of concentrate, fuel - reagent along the road, leading to ground - surface water contamination | Poor visibility on road - e.g, snow, fog AND Failure of Road Management Plan | None
An accident involving haul trucks could cause a significant spill of concentrate, fuel - reagent along the road, leading to ground - surface water contamination | Inclement weather AND Failure of Road Management Plan | None
An accident involving haul trucks could cause a significant spill of concentrate, fuel - reagent along the road, leading to ground - surface water contamination | Failure of communication system for road AND Failure of Road Management Plan | None
An accident involving haul trucks could cause a significant spill of concentrate, fuel - reagent along the road, leading to ground - surface water contamination AND Failure of Spill Equipment | None | Environmental damage
An accident involving haul trucks could cause a significant spill of concentrate, fuel - reagent along the road, leading to ground - surface water contamination AND Failure of Spill Equipment | None | Reputational damage
An accident involving haul trucks could cause a significant spill of concentrate, fuel - reagent along the road, leading to ground - surface water contamination AND Failure of Spill Equipment | None | Cost of cleanup
An accident involving haul trucks could cause a significant spill of concentrate, fuel - reagent along the road, leading to ground - surface water contamination AND Failure of Spill Equipment | None | Fines - penalties
An accident involving haul trucks could cause a significant spill of concentrate, fuel - reagent along the road, leading to ground - surface water contamination AND Failure of Spill Equipment | None | Non-compliance
An accident involving haul trucks could cause a significant spill of concentrate, fuel - reagent along the road, leading to ground - surface water contamination AND Failure of Spill Equipment | None | Deterioration in relationship with regulator
An accident involving haul trucks could cause a significant spill of concentrate, fuel - reagent along the road, leading to ground - surface water contamination AND Failure of Spill Response Training | None | Environmental damage
An accident involving haul trucks could cause a significant spill of concentrate, fuel - reagent along the road, leading to ground - surface water contamination AND Failure of Spill Response Training | None | Injuries/fatalities
An accident involving haul trucks could cause a significant spill of concentrate, fuel - reagent along the road, leading to ground - surface water contamination AND Failure of Spill Response Training | None | Reputational damage
An accident involving haul trucks could cause a significant spill of concentrate, fuel - reagent along the road, leading to ground - surface water contamination AND Failure of Spill Response Training | None | Cost of cleanup
An accident involving haul trucks could cause a significant spill of concentrate, fuel - reagent along the road, leading to ground - surface water contamination AND Failure of Spill Response Training | None | Fines - penalties
An accident involving haul trucks could cause a significant spill of concentrate, fuel - reagent along the road, leading to ground - surface water contamination AND Failure of Spill Response Training | None | Non-compliance
An accident involving haul trucks could cause a significant spill of concentrate, fuel - reagent along the road, leading to ground - surface water contamination AND Failure of Spill Response Training | None | Deterioration in relationship with regulator
An accident involving haul trucks could cause a significant spill of concentrate, fuel - reagent along the road, leading to ground - surface water contamination | Failure of communication system for road AND Failure of Truck maintenance | None
A significant malfunction in the water treatment system could lead to the discharge of untreated waters | Human error AND Failure of Inspection, monitoring - maintenance | None
A significant malfunction in the water treatment system could lead to the discharge of untreated waters | Catastrophic system failure AND Failure of Inspection, monitoring - maintenance | None
A significant malfunction in the water treatment system could lead to the discharge of untreated waters | Human error AND Failure of Water Treatment Plant Design to current standards | None
A significant malfunction in the water treatment system could lead to the discharge of untreated waters | Catastrophic system failure AND Failure of Water Treatment Plant Design to current standards | None
A significant malfunction in the water treatment system could lead to the discharge of untreated waters AND Failure of Water Treatment Plant back-up plants controls | None | Environmental damage
A significant malfunction in the water treatment system could lead to the discharge of untreated waters AND Failure of Water Treatment Plant back-up plants controls | None | Reputational damage
A significant malfunction in the water treatment system could lead to the discharge of untreated waters AND Failure of Water Treatment Plant back-up plants controls | None | Cost of cleanup
A significant malfunction in the water treatment system could lead to the discharge of untreated waters AND Failure of Water Treatment Plant back-up plants controls | None | Fines - penalties for non-compliance with water license
A significant malfunction in the water treatment system could lead to the discharge of untreated waters AND Failure of Water Treatment Plant back-up plants controls | None | Deterioration in relationship with regulator
A significant malfunction in the water treatment system could lead to the discharge of untreated waters AND Failure of Water Treatment Plant back-up plants controls | None | Delay in operations
A significant malfunction in the water treatment system could lead to the discharge of untreated waters AND Failure of Worker emergency response training | None | Environmental damage
A significant malfunction in the water treatment system could lead to the discharge of untreated waters AND Failure of Worker emergency response training | None | Reputational damage
A significant malfunction in the water treatment system could lead to the discharge of untreated waters AND Failure of Worker emergency response training | None | Cost of cleanup
A significant malfunction in the water treatment system could lead to the discharge of untreated waters AND Failure of Worker emergency response training | None | Fines - penalties for non-compliance with water license
A significant malfunction in the water treatment system could lead to the discharge of untreated waters AND Failure of Worker emergency response training | None | Deterioration in relationship with regulator
A significant malfunction in the water treatment system could lead to the discharge of untreated waters AND Failure of Worker emergency response training | None | Delay in operations
A significant malfunction in the water treatment system could lead to the discharge of untreated waters AND Failure of Back-up - Water Treatment Plant containment system | None | Environmental damage
A significant malfunction in the water treatment system could lead to the discharge of untreated waters AND Failure of Back-up - Water Treatment Plant containment system | None | Reputational damage
A significant malfunction in the water treatment system could lead to the discharge of untreated waters AND Failure of Back-up - Water Treatment Plant containment system | None | Cost of cleanup
A significant malfunction in the water treatment system could lead to the discharge of untreated waters AND Failure of Back-up - Water Treatment Plant containment system | None | Fines - penalties for non-compliance with water license
A significant malfunction in the water treatment system could lead to the discharge of untreated waters AND Failure of Back-up - Water Treatment Plant containment system | None | Deterioration in relationship with regulator
A significant malfunction in the water treatment system could lead to the discharge of untreated waters AND Failure of Back-up - Water Treatment Plant containment system | None | Delay in operations
Vehicle-wildlife interactions could cause collisions | Poor visibility on road - e.g., snow, fog AND Failure of Road Management Plan - e.g., communication system | None
Vehicle-wildlife interactions could cause collisions | Increased use of road AND Failure of Road Management Plan - e.g., communication system | None
Vehicle-wildlife interactions could cause collisions | Increased presence of wildlife in vicinity of road - mine sites AND Failure of Road Management Plan - e.g., communication system | None
Vehicle-wildlife interactions could cause collisions | Driver error AND Failure of Road Management Plan - e.g., communication system | None
Vehicle-wildlife interactions could cause collisions | Failure of communication system for road AND Failure of Road Management Plan - e.g., communication system | None
Vehicle-wildlife interactions could cause collisions | Poor visibility on road - e.g., snow, fog AND Failure of Road design considerations to facilitate wildlife movement - slides slopes, road width, slope surface, visibility | None
Vehicle-wildlife interactions could cause collisions | Increased presence of wildlife in vicinity of road - mine sites AND Failure of Road design considerations to facilitate wildlife movement - slides slopes, road width, slope surface, visibility | None
Vehicle-wildlife interactions could cause collisions AND Failure of Spill Contigency - Response plans | None | Loss of product
Vehicle-wildlife interactions could cause collisions | Poor visibility on road - e.g., snow, fog AND Failure of Driver training | None
Vehicle-wildlife interactions could cause collisions | Increased use of road AND Failure of Driver training | None
Vehicle-wildlife interactions could cause collisions | Increased presence of wildlife in vicinity of road - mine sites AND Failure of Driver training | None
Vehicle-wildlife interactions could cause collisions | Driver error AND Failure of Driver training system | None
Vehicle-wildlife interactions could cause collisions | Failure of communication system for road AND Failure of Driver training | None
Vehicle-wildlife interactions could cause collisions AND Failure of Emergency shelters | None | - Vehicular Injuries/fatalities
Failure - collision of aircraft could lead to injuries - loss of human life | Failure of aircraft/equipment AND Failure of Regular aircraft inspection, maintenance - record keeping | None
Failure - collision of aircraft could lead to injuries - loss of human life AND Failure of Regular aircraft inspection, maintenance - record keeping | None | Reputational damage
Failure - collision of aircraft could lead to injuries - loss of human life AND Failure of Regular aircraft inspection, maintenance - record keeping | None | Cost of compensation
Failure - collision of aircraft could lead to injuries - loss of human life | Inclement weather AND Failure of Adherence to aviation standards - codes | None
Failure - collision of aircraft could lead to injuries - loss of human life | Human error AND Failure of Adherence to aviation standards - codes | None
Failure - collision of aircraft could lead to injuries - loss of human life | Failure of aircraft/equipment AND Failure of Adherence to aviation standards - codes | None
Failure - collision of aircraft could lead to injuries - loss of human life AND Failure of Adherence to aviation standards - codes | None | - Vehicular Injuries/fatalities
Failure - collision of aircraft could lead to injuries - loss of human life AND Failure of Adherence to aviation standards - codes | None | Reputational damage
Failure - collision of aircraft could lead to injuries - loss of human life AND Failure of Adherence to aviation standards - codes | None | Cost of compensation
Failure - collision of aircraft could lead to injuries - loss of human life | Inclement weather AND Failure of Annual safety audit | None
Failure - collision of aircraft could lead to injuries - loss of human life | Human error AND Failure of Annual safety audit | None
Failure - collision of aircraft could lead to injuries - loss of human life | Failure of aircraft/equipment AND Failure of Annual safety audit | None
Failure - collision of aircraft could lead to injuries - loss of human life AND Failure of Annual safety audit | None | Reputational damage
Failure - collision of aircraft could lead to injuries - loss of human life AND Failure of Annual safety audit | None | Cost of compensation
Failure - collision of aircraft could lead to injuries - loss of human life | Inclement weather AND Failure of Camp - pilot communication | None
Failure - collision of aircraft could lead to injuries - loss of human life | Human error AND Failure of Camp - pilot communication | None
Failure - collision of aircraft could lead to injuries - loss of human life | Failure of aircraft/equipment AND Failure of Camp - pilot communication | None
Failure - collision of aircraft could lead to injuries - loss of human life AND Failure of Camp - pilot communication | None | - Vehicular Injuries/fatalities
Failure - collision of aircraft could lead to injuries - loss of human life AND Failure of Camp - pilot communication | None | Reputational damage
Failure - collision of aircraft could lead to injuries - loss of human life AND Failure of Camp - pilot communication | None | Cost of compensation
Failure - collision of aircraft could lead to injuries - loss of human life - Aircraft Collision Emergency Response Plan | None | - Vehicular Injuries/fatalities
Failure - collision of aircraft could lead to injuries - loss of human life - Aircraft Collision Emergency Response Plan | None | Reputational damage
Failure - collision of aircraft could lead to injuries - loss of human life - Aircraft Collision Emergency Response Plan | None | Cost of compensation
Incomplete marine bathymetric, hydrographic, ice, wind - wave data could cause navigational - safety issues for Project shipping | Lack of detailed information on marine environment - physical processes to ensure safe navigation along shipping routes AND Failure of Comprehensive marine baseline studies | None
Incomplete marine bathymetric, hydrographic, ice, wind - wave data could cause navigational - safety issues for Project shipping | Failure of navigation system AND Failure of Comprehensive marine baseline studies | None
Incomplete marine bathymetric, hydrographic, ice, wind - wave data could cause navigational - safety issues for Project shipping AND Failure of Comprehensive marine baseline studies | None | Loss of vessel
Incomplete marine bathymetric, hydrographic, ice, wind - wave data could cause navigational - safety issues for Project shipping AND Failure of Comprehensive marine baseline studies | None | Loss of product
Incomplete marine bathymetric, hydrographic, ice, wind - wave data could cause navigational - safety issues for Project shipping AND Failure of Comprehensive marine baseline studies | None | Loss of Cargo
Incomplete marine bathymetric, hydrographic, ice, wind - wave data could cause navigational - safety issues for Project shipping AND Failure of Comprehensive marine baseline studies | None | Injuries/fatalities
Incomplete marine bathymetric, hydrographic, ice, wind - wave data could cause navigational - safety issues for Project shipping AND Failure of Comprehensive marine baseline studies | None | Delay in shipping schedule
Incomplete marine bathymetric, hydrographic, ice, wind - wave data could cause navigational - safety issues for Project shipping AND Failure of Comprehensive marine baseline studies | None | Environmental damage
Incomplete marine bathymetric, hydrographic, ice, wind - wave data could cause navigational - safety issues for Project shipping AND Failure of Comprehensive marine baseline studies | None | Reputational damage
Incomplete marine bathymetric, hydrographic, ice, wind - wave data could cause navigational - safety issues for Project shipping | Lack of detailed information on marine environment - physical processes to ensure safe navigation along shipping routes AND Failure of Bathymetric mapping of shipping corridors | None
Incomplete marine bathymetric, hydrographic, ice, wind - wave data could cause navigational - safety issues for Project shipping | Failure of navigation system AND Failure of Bathymetric mapping of shipping corridors | None
Incomplete marine bathymetric, hydrographic, ice, wind - wave data could cause navigational - safety issues for Project shipping AND Failure of Bathymetric mapping of shipping corridors | None | Loss of vessel
Incomplete marine bathymetric, hydrographic, ice, wind - wave data could cause navigational - safety issues for Project shipping AND Failure of Bathymetric mapping of shipping corridors | None | Loss of product
Incomplete marine bathymetric, hydrographic, ice, wind - wave data could cause navigational - safety issues for Project shipping AND Failure of Bathymetric mapping of shipping corridors | None | Loss of Cargo
Incomplete marine bathymetric, hydrographic, ice, wind - wave data could cause navigational - safety issues for Project shipping AND Failure of Bathymetric mapping of shipping corridors | None | Injuries/fatalities
Incomplete marine bathymetric, hydrographic, ice, wind - wave data could cause navigational - safety issues for Project shipping AND Failure of Bathymetric mapping of shipping corridors | None | Delay in shipping schedule
Incomplete marine bathymetric, hydrographic, ice, wind - wave data could cause navigational - safety issues for Project shipping AND Failure of Bathymetric mapping of shipping corridors | None | Environmental damage
Incomplete marine bathymetric, hydrographic, ice, wind - wave data could cause navigational - safety issues for Project shipping AND Failure of Bathymetric mapping of shipping corridors | None | Reputational damage
Incomplete marine bathymetric, hydrographic, ice, wind - wave data could cause navigational - safety issues for Project shipping | Failure of navigation system AND Failure of Regular inspection - maintenance of vessel - control systems | None
Incomplete marine bathymetric, hydrographic, ice, wind - wave data could cause navigational - safety issues for Project shipping | Loss of power AND Failure of Regular inspection - maintenance of vessel - control systems | None
Incomplete marine bathymetric, hydrographic, ice, wind - wave data could cause navigational - safety issues for Project shipping AND Failure of Regular inspection - maintenance of vessel - control systems | None | Loss of vessel
Incomplete marine bathymetric, hydrographic, ice, wind - wave data could cause navigational - safety issues for Project shipping AND Failure of Regular inspection - maintenance of vessel - control systems | None | Loss of product
Incomplete marine bathymetric, hydrographic, ice, wind - wave data could cause navigational - safety issues for Project shipping AND Failure of Regular inspection - maintenance of vessel - control systems | None | Loss of Cargo
Incomplete marine bathymetric, hydrographic, ice, wind - wave data could cause navigational - safety issues for Project shipping AND Failure of Regular inspection - maintenance of vessel - control systems | None | Injuries/fatalities
Incomplete marine bathymetric, hydrographic, ice, wind - wave data could cause navigational - safety issues for Project shipping AND Failure of Regular inspection - maintenance of vessel - control systems | None | Delay in shipping schedule
Incomplete marine bathymetric, hydrographic, ice, wind - wave data could cause navigational - safety issues for Project shipping AND Failure of Regular inspection - maintenance of vessel - control systems | None | Environmental damage
Incomplete marine bathymetric, hydrographic, ice, wind - wave data could cause navigational - safety issues for Project shipping AND Failure of Regular inspection - maintenance of vessel - control systems | None | Reputational damage
Incomplete marine bathymetric, hydrographic, ice, wind - wave data could cause navigational - safety issues for Project shipping | Lack of detailed information on marine environment - physical processes to ensure safe navigation along shipping routes AND Failure of Collision Risk Management System - Prevention | None
Incomplete marine bathymetric, hydrographic, ice, wind - wave data could cause navigational - safety issues for Project shipping | Failure of navigation system AND Failure of Collision Risk Management System - Prevention | None
Incomplete marine bathymetric, hydrographic, ice, wind - wave data could cause navigational - safety issues for Project shipping | Inclement weather AND Failure of Collision Risk Management System - Prevention | None
Incomplete marine bathymetric, hydrographic, ice, wind - wave data could cause navigational - safety issues for Project shipping | Poor Ice Conditions AND Failure of Collision Risk Management System - Prevention | None
Incomplete marine bathymetric, hydrographic, ice, wind - wave data could cause navigational - safety issues for Project shipping | Human error AND Failure of Collision Risk Management System - Prevention | None
Incomplete marine bathymetric, hydrographic, ice, wind - wave data could cause navigational - safety issues for Project shipping | Loss of power AND Failure of Collision Risk Management System - Prevention | None
Incomplete marine bathymetric, hydrographic, ice, wind - wave data could cause navigational - safety issues for Project shipping AND Failure of Collision Risk Management System - Emergency Response | None | Loss of vessel
Incomplete marine bathymetric, hydrographic, ice, wind - wave data could cause navigational - safety issues for Project shipping AND Failure of Collision Risk Management System - Emergency Response | None | Loss of product
Incomplete marine bathymetric, hydrographic, ice, wind - wave data could cause navigational - safety issues for Project shipping AND Failure of Collision Risk Management System - Emergency Response | None | Loss of Cargo
Incomplete marine bathymetric, hydrographic, ice, wind - wave data could cause navigational - safety issues for Project shipping AND Failure of Collision Risk Management System - Emergency Response | None | Injuries/fatalities
Incomplete marine bathymetric, hydrographic, ice, wind - wave data could cause navigational - safety issues for Project shipping AND Failure of Collision Risk Management System - Emergency Response | None | Delay in shipping schedule
Incomplete marine bathymetric, hydrographic, ice, wind - wave data could cause navigational - safety issues for Project shipping AND Failure of Collision Risk Management System - Emergency Response | None | Environmental damage
Incomplete marine bathymetric, hydrographic, ice, wind - wave data could cause navigational - safety issues for Project shipping AND Failure of Collision Risk Management System - Emergency Response | None | Reputational damage
Incomplete marine bathymetric, hydrographic, ice, wind - wave data could cause navigational - safety issues for Project shipping AND Failure of Collision Risk Management System - Contingency Procedures | None | Loss of vessel
Incomplete marine bathymetric, hydrographic, ice, wind - wave data could cause navigational - safety issues for Project shipping AND Failure of Collision Risk Management System - Contingency Procedures | None | Loss of product
Incomplete marine bathymetric, hydrographic, ice, wind - wave data could cause navigational - safety issues for Project shipping AND Failure of Collision Risk Management System - Contingency Procedures | None | Loss of Cargo
Incomplete marine bathymetric, hydrographic, ice, wind - wave data could cause navigational - safety issues for Project shipping AND Failure of Collision Risk Management System - Contingency Procedures | None | Injuries/fatalities
Incomplete marine bathymetric, hydrographic, ice, wind - wave data could cause navigational - safety issues for Project shipping AND Failure of Collision Risk Management System - Contingency Procedures | None | Delay in shipping schedule
Incomplete marine bathymetric, hydrographic, ice, wind - wave data could cause navigational - safety issues for Project shipping AND Failure of Collision Risk Management System - Contingency Procedures | None | Environmental damage
Incomplete marine bathymetric, hydrographic, ice, wind - wave data could cause navigational - safety issues for Project shipping AND Failure of Collision Risk Management System - Contingency Procedures | None | Reputational damage
Incomplete marine bathymetric, hydrographic, ice, wind - wave data could cause navigational - safety issues for Project shipping | Lack of detailed information on marine environment - physical processes to ensure safe navigation along shipping routes AND Failure of Shipping Management Plan | None
Incomplete marine bathymetric, hydrographic, ice, wind - wave data could cause navigational - safety issues for Project shipping | Inclement weather AND Failure of Shipping Management Plan | None
Incomplete marine bathymetric, hydrographic, ice, wind - wave data could cause navigational - safety issues for Project shipping | Poor Ice Conditions AND Failure of Shipping Management Plan | None
Incomplete marine bathymetric, hydrographic, ice, wind - wave data could cause navigational - safety issues for Project shipping AND Failure of Shipping Management Plan | None | Delay in shipping schedule
Incomplete marine bathymetric, hydrographic, ice, wind - wave data could cause navigational - safety issues for Project shipping AND Failure of Marine Spill Reponse Plan | None | Loss of product
Incomplete marine bathymetric, hydrographic, ice, wind - wave data could cause navigational - safety issues for Project shipping AND Failure of Marine Spill Reponse Plan | None | Loss of Cargo
Incomplete marine bathymetric, hydrographic, ice, wind - wave data could cause navigational - safety issues for Project shipping AND Failure of Marine Spill Reponse Plan | None | Delay in shipping schedule
Incomplete marine bathymetric, hydrographic, ice, wind - wave data could cause navigational - safety issues for Project shipping AND Failure of Marine Spill Reponse Plan | None | Environmental damage
Incomplete marine bathymetric, hydrographic, ice, wind - wave data could cause navigational - safety issues for Project shipping AND Failure of Marine Spill Reponse Plan | None | Reputational damage