## Sheet1
acid sulphate soils are oxidised creating acidity | Cause
acidified soil | Consequence
acidified water | Consequence
adequate supervision of rehabilitation activities so that landforms and soil profiles are created as designed [control] | PreventionControl
aer includes discussion on closure and rehabilitation [control] | PreventionControl
agree required standard for infrastructure in consultation with landowners and include within mcp [control] | PreventionControl
agricultural productivity is less than pre-mining levels | RiskEvent
agricultural productivity is reduced | Consequence
altered water regime [ie local drought] | Cause
amenity / use of land is compromised | Consequence
annual review of mcp and cost estimates, with continual improvement in the level of detail contained. [control] | PreventionControl
area is unexpectedly waterlogged and seedlings die due to waterlogging | Cause_Consequence_RiskEvent
arson [bushfire data] | Cause
assumptions used in cost estimates to be included within the mcp and reviewed annually. [control] | PreventionControl
assumptions used prove to be inaccurate | Cause
autumn prescribed burn or wildfire [ecosystem trajectory model] | Cause
backfill in mine pits consolidation pattern is unknown or not as expected | Cause_RiskEvent
backfill of mine pits with sand or overburden/tails locally changes the groundwater behaviour , i.e. localised waterlogging / flooding occurs, or soil suffers springtime 'drought' | Cause
careful reconstruction of soil profile including 150mm of topsoil, 300mm subsoil and minimum of 2500mm of overburden [control] | PreventionControl
change to post-mining landuse | Cause_Consequence
changes to surface water drainage if not corrected | Consequence
closure cost estimates and provisioning includes removal of infrastructure [control] | PreventionControl
closure cost estimates and provisioning is reviewed and updated on annual basis [control] | PreventionControl
closure cost estimates are prepared by suitably qualified professionals experienced in produce mine closure cost estimates [control] | PreventionControl
closure due to government policy | Cause
closure implementation not planned for | Cause_Consequence
closure implementation schedule not based on learnings from progressive rehabilitation | Cause
compensation [cost] to future land users if structures fail | Consequence
compliance failure [declared weeds, revegetation composition | Consequence
conservation offset areas are not sustainable | RiskEvent
contaminated sites | RiskEvent
contractual dispute with landowners due to inability to hand back land in the agrred condition within agreed timeframe | Consequence
cost of control | Consequence
cost of rework | Cause_Consequence
cost overrun due to increased duration of activities. | Cause_Consequence
decision making stakeholder' review and acceptance of how obligations are being met, prior to closure. [control] | PreventionControl
decontaminate any hydrocarbon contamination identified [control] | MitigationControl
deficient establishment from applied seed or high levels of weed invasion | Consequence
deficient establishment from applied seed or high levels of weed invasion [ecosystem trajectory model] | Cause
delay in handover / relinquishment of land until infrastructure removed | Consequence
delay to relinquishing land tenure, involving management time and cost | Consequence
dense scrub dominated by eucalypt species [>2,500 stems/ha] with low to moderate species richness [<80% of forest controls] allows dense [>2,500 stems/ha] sapling/pole stand with sparse understorey, moderate fuel loads, and low species richness to grow [ecosystem trajectory model] | RiskEvent
design landforms and soil profiles do not support agreed landuse | Cause
design soils profiles for each rehab block with at least 15cm of topsoil and 1 m of subsoil materials on top of sand tails [control] | PreventionControl
deterioration of public reputation | Consequence
develop and obtain landholder agreement to detailed landform designs. [control] | PreventionControl
dieback kills established vegetation | Cause
dieback management measures as defined in rehilitation management plans for rehabilated area [control] | PreventionControl
diesel [or other hydrocarbon] spill or leak | Cause
dry plant tailings is capped with 5 metres of sand, clay, overburden and/or soil [control] | PreventionControl
dry plant tails not adequately covered with low radiation soils | Cause
economic prosperity of local region compromised [social] | Consequence_RiskEvent
elevated radiation levels at the final landform surface | Consequence
erosion on site | Cause_RiskEvent
excessive establishment from applied seed [ecosystem trajectory model] | Cause
failure to get bonds released | Consequence
failure to identify, monitor and control weeds | Cause
failure to implement / undertake legal obligations | Cause
failure to plan to meet legal obligations | Cause
failure to plan to reinstate all required infrastructure | Cause
failure to understand, or difference in interpretation, of obligations. | Cause
feedback from actual rehabilitation expenditure is utilised in updates to rehabilitation cost estimates and provisioning. [control] | PreventionControl
fire damaged eucalypts [poor tree form] with regenerating understorey [ecosystem trajectory model] | Consequence_RiskEvent
flooding from high rainfall events [rainfall - water models] | Cause
future success of company compromised [social] | Consequence
geotechnical stability [subsidence] | Cause_RiskEvent
grade of ore not sufficient | Cause
groundwater [does not return similar to pre-mining functioning] | RiskEvent
groundwater flows and quality not considered in rehabilitation planning | Cause_Consequence
groundwater investigation, modelling and assessment undertaken, including post-mining groundwater recovery [control] | MitigationControl_PreventionControl
groundwater monitoring includes neighbouring landowners bores [control] | MitigationControl
groundwater patterns and flows on site not understood | Cause_Consequence
human injury or death | Consequence_RiskEvent
hydrocarbon contaminated soil | Consequence
hydrocarbon contaminated water | Consequence
impact on neighbouring landowners and community due ongoing delays [e.g. ongoing road closures, noise impacts, irrigation channel control] | Consequence
impacts on neighbours [e.g. road reserves, adjoining landowners] | Cause_Consequence
implement good practice pasture management practices [control] | PreventionControl
implement weed control in agricultural areas [control] | MitigationControl
implementation of the ass managment plan. [control] | MitigationControl
inadequate financial provision set aside for decommissioning and rehabilitation | Cause_RiskEvent
increased cost of closure | Consequence_RiskEvent
indigenous j/v threatened | Consequence
infrastructure to be reinstated is clearly identified and costed for within mcp [control] | PreventionControl
inrush | Cause
inspection and adaptive management [response to weeds, grazing pressure, erosion] [control] | MitigationControl
job losses in employees [social] | Consequence
kangaroo fencing and managed culling [control] | PreventionControl
keep no less than 100mm of subsoil when ore is to surface [control] | PreventionControl
keep topsoil and subsoil for use in rehab [control] | PreventionControl
land is monitored by company for at least 3 years prior to return to landowner [control] | MitigationControl_PreventionControl
land not able to sustain target agricultural vegetation growth | Consequence
land not able to sustain target native vegetation growth | Cause_Consequence_RiskEvent
landform and soil profile design based on industry experience, good science and site specific information [control] | PreventionControl
landform design does not accommodate surface water flows of site | Cause_RiskEvent
landforms [do not support agreed landuses] | Consequence_RiskEvent
landforms and soil profiles are not created | Cause
leak amd | Cause
legal mechanisms for implementing management controls of offset areas are established by company prior to land transfer [control] | MitigationControl
legal obligations and commitments identified and included within mcp. [control] | PreventionControl
legal obligations and commitments not achieved | RiskEvent
lightning strikes [bushfire data] | Cause
loss of access to future deposits | Consequence
low rainfall events [rainfall - water models] | Cause
low rainfall seasonal conditions | Cause_RiskEvent
map rehabilitated mine pit backfill types and depth [control] | PreventionControl
mcp and rehabilitation schedule annually updated [control] | PreventionControl
mcp includes tracking of how obligations and commitments are being met. [control] | PreventionControl
measure soil properties and agricultural productivity [pre and post mining] [control] | PreventionControl
mine closes early | Consequence_RiskEvent
mine filled with water | Cause_RiskEvent
mine owner financial difficulties during mine expansion phase | Cause
mined out road tenure [i.e. areas where post-mining landuse is road reserve] is backfilled with materials that meet compaction specifications [control] | PreventionControl
mining infrastructure removal [failure to completely remove] | Cause_Consequence_RiskEvent
monitor/measure performance of landforms and soil profiles in rehabilitated areas, and incorporate any learnings/lessons into future rehabilitation design [control] | PreventionControl
neighbours water bores dry up at or post-closure | Consequence
not all infrastructure identified and costed | Cause
offset strategy shall incorporate a management plan to address issues related to dieback, weed invasion, feral animal exclusion, fire management [control] | PreventionControl
offset strategy shall incorporate areas of established bushland [control] | PreventionControl
ongoing consultation with landowners regarding handback of land and contractual obligations [control] | MitigationControl
ongoing consultation with stakeholders regarding planned implementation of closure [control] | MitigationControl
ongoing liability to public safety for any infrastructure left on site | Cause_Consequence
overtopping of dams from high rainfall events [rainfall - water models] | Cause
ownership change | Cause
performance of landforms and soil profiles not well understood and assumptions prove incorrect | Cause_Consequence_RiskEvent
planted in areas with too little soil water available | Cause_Consequence_RiskEvent
pole-sized eucalypts with dense regenerating acacia understorey [>2 legumes/m2], moderate to high species richness [>50% of forest controls], and greater than 5% tree deaths following burning [ecosystem trajectory model] | RiskEvent
pole-sized eucalypts with regenerating understorey with low species richness [<50% of forest controls] [ecosystem trajectory model] | RiskEvent
poor pasture management practices [e.g. fertiliser use, weed control, stock management] | Cause
poorly landscaped pit with active erosion*, unblasted caprock*, less than 90% topsoil cover*, and or shallow ripping* [ecosystem trajectory model] | RiskEvent
post-mining land fails to be as productive as pre-mining land | Cause_Consequence
post-mining land owners build structures on backfilled mining voids | Cause
post-mining soil profiles do not support productive pastures | Cause
post-mining soil profiles on coastal plain include 'duplex' soils within top 1 metre, which recreates perched watertable which supplies water for agricultural species [control] | MitigationControl
pre- and post-mining radiation surveys [control] | MitigationControl
pre-disturbance surveys [control] | PreventionControl
price of ore not sufficient | Cause
prosecution with associated penalties. | Consequence
rabbit control baiting [control] | PreventionControl
re-rehabilitation [ecosystem trajectory model] [control] | PreventionControl
recovery/sale value assumed in cost estimate overly optimistic. | Cause
reduced land value at time of sale | Cause_Consequence
regeneration over time [ecosystem trajectory model] [control] | MitigationControl
regular inspection and rework to correct smaller issues before esculation to significant damage [control] | MitigationControl
regular weed monitoring [control] | PreventionControl
rehabilitation not able to be achieved [resulting in compliance issue, loss of licence to operate and/or difficulty getting access to new areas] | Consequence
reinstated instructure not build to required standard | Cause
reinstated roads and road reserves road do not achieve required completion standards | RiskEvent
relandscape pit [ecosystem trajectory model] [control] | PreventionControl
removal and spraying of weeds in rehabilitated native vegetation areas [control] | MitigationControl_PreventionControl
reseed or plant more recalcitrant species [ecosystem trajectory model] [control] | MitigationControl_PreventionControl
reserves at depth | Cause
restrictions to post-mining agricultural management [e.g. hazards to livestock or restriction to vehicle and equipment movement] | Consequence
ripping shallow or off contour, unblasted caprock, or inadequate soil return [ecosystem trajectory model] | Cause
saline ground water contaminates surface soils | Cause
schedule is not location specific | Cause
seedlings area planted and tree guards installed [control] | PreventionControl
significant safety event e.g. cyanide spill | Cause
soil profiles are are established based on recommendation and findings from pre mining soil assessment [control] | PreventionControl
sparse scrub vegetation with low eucalypt [<500 stems/ha]* or legume [<0.5 m2]* density and low species richness [<50% of forest controls]* [ecosystem trajectory model] | Consequence
sparse vegetation cover with low eucalypt [<500 stems/ha]* or legume [<0.5 m2]* density and low species richness [<50% of forest controls]* or high weed density* [ecosystem trajectory model] | RiskEvent
specific items required at and post-closure are not costed | Cause_Consequence
spring prescribed burn [ecosystem trajectory model] | Cause
state government pursues company owners for costs | Consequence
stock or vermin eat seedlings | Cause
structural failure of road [built over mine pit] | Consequence
stunted sapling eucalypts with sparse understorey, erosion gullies, and drought deaths [ecosystem trajectory model] | Cause_Consequence
subsidence monitoring and rework to correct [control] | MitigationControl
supplementary seeding or planting of understorey species [ecosystem trajectory model] [control] | MitigationControl
sustainability of native revegetation is not achieved | Consequence_RiskEvent
thin rehabilitated areas to 750 stems/ha [500–1,000 stems/ha] [ecosystem trajectory model] [control] | MitigationControl
time to complete mine closure and revegetation works extends beyond scheduled program | RiskEvent
traditional owner objection [social] | Cause
underestimate of closure costs | Cause
undertake hydrocarbon site contamination assessment [control] | PreventionControl
undertake infill / secondary plantings as required to acheive required vegetation densities [control] | PreventionControl
unstable and unvegetated surface soils [i.e. sands] and creeklines | Cause
update and maintain legal compliance register [control] | PreventionControl
utilisation of road standards [control] | PreventionControl
vegetation species are selected according to ageed revegetation species criteria [control] | MitigationControl_PreventionControl
vegetation succumbs to disease | Cause
water and soil monitoring to detect acidification resulting from ass [control] | PreventionControl
weeds [agricultural, environmental and declared] | RiskEvent
when economics are marginal avoid erosion-prone area [control] | PreventionControl
wildfire [ecosystem trajectory model] | Cause_RiskEvent